## Overview
TWEDAR - Project Progress Tracker
AI-Enabled Smart Wedding Planning Platform
HOW TO USE THIS SPREADSHEET
1. Each tab represents a major feature module from the project document.
2. Status colors: GREEN = Done, YELLOW = In Progress, RED = Not Started.
3. Column D shows overall status. Columns E & F show backend/frontend separately.
4. Column H describes exactly what remains to be built for each feature.
5. Column I shows priority (Must Have / Should Have / Could Have).
6. Column J references the section in the project document PDF.
7. Use the summary table below to see completion % per module.
COLOR LEGEND
Done
In Progress
Not Started
PROJECT SUMMARY
Module | Total | Done | In Progress | Not Started | Completion %
1. Auth & User Mgmt | 18 | 14 | 3 | 1 | 78%
2. Vendor Management | 24 | 21 | 1 | 2 | 88%
3. Real-Time Comms | 16 | 13 | 0 | 3 | 81%
4. Budgeting & Expense | 8 | 0 | 0 | 8 | 0%
5. AI Recommendations | 10 | 0 | 0 | 10 | 0%
6. Booking & Scheduling | 8 | 0 | 0 | 8 | 0%
7. Payment Integration | 8 | 0 | 0 | 8 | 0%
8. Review & Feedback | 8 | 0 | 0 | 8 | 0%
9. Admin & Analytics | 12 | 2 | 4 | 6 | 17%
10. Couple Planning | 11 | 0 | 1 | 10 | 0%
11. Non-Functional | 16 | 1 | 6 | 9 | 6%
TOTAL | 139 | 51 | 15 | 73 | 37%
PROJECT METADATA
Project: | Twedar - AI-Enabled Smart Wedding Planning Platform
Team: | Chera Mihretu, Abdi Esayas, Surafel Takele, Tamirat Kebede, Hanamariam Mesfin
University: | Adama Science and Technology University
Advisor: | Mr. Anteneh
Generated: | April 2026
Document: | Twedar GC Project (110 pages)

## 1. Auth & User Mgmt
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Registration & Login
A-01 | Email/Password Registration | Users register with email and password. Password hashed with bcrypt. Role selected at registration. | Done | Done | Done | Better Auth handles registration with accountType field mapped to role. Frontend register page with role selector. |  | Must Have | 3.2.1
A-02 | Email Verification | System sends verification email after registration. User clicks link to verify. | Done | Done | Done | Better Auth sendVerificationEmail configured with Nodemailer. Frontend /verify-email and /check-email pages. |  | Must Have | 3.2.1
A-03 | Email/Password Login | Authenticated login with session cookie creation. | Done | Done | Done | Better Auth signIn.email. Frontend login page with redirect to role dashboard. |  | Must Have | 3.4.2 UC2
A-04 | Google OAuth (Couples) | Social login via Google for quick couple signup. | Done | Done | Done | Better Auth socialProviders.google configured. Frontend redirects to /api/auth/social/google. Callback page handles edge cases. |  | Must Have | 3.2.1
A-05 | Apple OAuth (Couples) | Social login via Apple for quick couple signup. | Done | Done | Done | Better Auth socialProviders.apple configured. Frontend callback handles Apple flow. |  | Should Have | 3.2.1
A-06 | Password Reset / Forgot Password | Email-based password reset flow. | Done | Done | Done | Better Auth forgetPassword + resetPassword. Frontend forget-password and reset-password pages. |  | Must Have | 3.2.1
Session & Security
A-07 | HTTP-Only Session Cookies | Secure session management without client-side token exposure. | Done | Done | Done | Better Auth configured with httpOnly cookies, 30-day expiry, SameSite lax/none, secure in production. |  | Must Have | 4.11.1
A-08 | RBAC Middleware | Role-based access control enforced at API level. | Done | Done | Done | requireAuth + requireRole middleware in auth feature. Frontend AuthGuard component checks session + role. |  | Must Have | 4.11.4
A-09 | Session Validation on App Load | Check session status on initial page load for routing. | Done | Done | Done | Frontend useSession hook from better-auth/react. AuthGuard validates on mount. |  | Must Have | 4.11.1
A-10 | 401 Global Handling | Redirect to login on unauthorized responses. | Done | Done | Done | apiFetch in auth.service.ts checks 401 and redirects to /login. |  | Must Have | 4.11.1
Role Management
A-11 | Couple Role | Standard user with access to wedding planning features. | Done | Done | Done | Role 'couple' created at registration. Couple layout with dashboard shell. |  | Must Have | 4.11.4
A-12 | Vendor Owner Role | Organization owner with full vendor dashboard access. | Done | Done | In Progress | Backend auto-creates Organization on vendor registration. Frontend has vendor layout but no org management UI. | Add organization member list UI, staff management. | Must Have | 4.11.4
A-13 | Vendor Staff Role | Organization member with limited access (chat, schedule). | In Progress | Done | Not Started | Better Auth Organization plugin configured with owner/member roles and permissions. No frontend staff view. | Build vendor staff invitation UI, restricted staff dashboard. | Should Have | 4.11.4
A-14 | Super Admin Role | Full system access for platform management. | Done | Done | In Progress | Admin plugin configured. Admin layout exists with vendor moderation. Missing users/reports/settings pages. | Build admin users list, reports, and settings pages. | Must Have | 4.11.4
A-15 | Content Moderator Role | Limited admin privileges assigned by Super Admin. | In Progress | In Progress | Not Started | Admin plugin supports role assignment. No dedicated moderator UI or role differentiation in frontend. | Add moderator role assignment UI, restricted admin views. | Could Have | 4.11.4
Profile Management
A-16 | Couple Profile Update | Couples update personal info, wedding preferences. | In Progress | In Progress | Not Started | Better Auth user fields exist. No dedicated couple profile/preferences page. | Build couple profile page with wedding date, theme, location fields. | Must Have | 3.4.2 UC3
A-17 | Vendor Profile Management | Vendors manage business info, services, pricing. | Done | Done | Done | Full vendor profile CRUD with setup wizard page. |  | Must Have | 3.4.2 UC3
A-18 | Admin Profile/Settings | Admin can update system settings. | Not Started | Not Started | Not Started | No admin settings implementation. | Build admin settings page and backend config API. | Could Have | 3.4.2 UC3

## 2. Vendor Management
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Vendor Profile & Listing
V-01 | Vendor Registration | Vendor registers and auto-creates organization. | Done | Done | Done | Registration with accountType=vendor triggers org creation via databaseHooks. |  | Must Have | 3.2.2, US-V-001
V-02 | Business Profile Creation | Vendor creates profile with business name, category, description, location. | Done | Done | Done | POST /api/v1/vendor/profile. Frontend setup wizard with all fields. |  | Must Have | 3.2.2
V-03 | Service & Pricing Packages | Vendor defines service types and pricing ranges. | Done | Done | Done | vendor_profiles table has price_range_min/max, category. Setup form includes pricing section. |  | Must Have | 3.2.2
V-04 | Location with Map | Vendor sets location with latitude/longitude on map. | Done | Done | Done | Backend stores lat/long with btree_gist index. Frontend Leaflet map picker component. |  | Must Have | 3.2.2
V-05 | Portfolio Upload | Vendor uploads images/videos showcasing previous work. | In Progress | Done | In Progress | Backend has portfolio JSONB field in vendor_profiles. Frontend vendor nav has Portfolio link but no dedicated page. | Build dedicated portfolio page with media grid, upload/delete functionality. | Must Have | 3.4.2 UC11
V-06 | Social Links | Vendor adds social media links to profile. | Done | Done | Done | social_links JSONB field in vendor_profiles. Setup form includes social links section. |  | Could Have | 3.2.2
V-07 | Vendor Availability/Schedule | Vendor sets available dates and working hours. | Not Started | Not Started | Not Started | No availability/calendar implementation. | Build availability schema, API endpoints, and calendar UI for vendors. | Should Have | 3.2.2
Document & Verification
V-08 | Document Upload | Vendor uploads business license, ID, certifications. | Done | Done | Done | POST /api/v1/vendor/documents with Supabase storage. Frontend DocumentUpload component. |  | Must Have | 3.2.3, US-V-002
V-09 | Document Delete | Vendor can remove uploaded documents. | Done | Done | Done | DELETE /api/v1/vendor/documents/:documentId. |  | Must Have | 3.2.3
V-10 | Submit for Verification | Vendor submits profile for admin review. | Done | Done | Done | POST /api/v1/vendor/profile/submit. Status transitions via status-machine.ts. |  | Must Have | 3.2.3
V-11 | Verification Status Display | Vendor sees their current verification status. | Done | Done | Done | VendorStatusBanner component shows pending/verified/rejected state. |  | Must Have | 3.2.3, US-V-003
V-12 | Resubmission After Rejection | Vendor fixes issues and resubmits with admin feedback. | Done | Done | Done | Status machine allows draft->pending_verification transition after rejection. |  | Should Have | 3.2.3, US-V-004
Admin Vendor Actions
V-13 | List All Vendors (Admin) | Admin views all registered vendors with status. | Done | Done | Done | GET /api/v1/admin/vendors. Admin vendors list page with status badges. |  | Must Have | 3.4.2 UC14
V-14 | Approve Vendor | Admin approves vendor after document review. | Done | Done | Done | POST /api/v1/admin/vendors/:id/approve. Admin detail page with approve button. |  | Must Have | 3.4.2 UC14
V-15 | Reject Vendor | Admin rejects vendor with reason. | Done | Done | Done | POST /api/v1/admin/vendors/:id/reject with reason. ReasonModal component. |  | Must Have | 3.4.2 UC14
V-16 | Suspend Vendor | Admin suspends vendor for policy violations. | Done | Done | Done | POST /api/v1/admin/vendors/:id/suspend. ConfirmDialog component. |  | Must Have | 4.11.3
V-17 | Reinstate Vendor | Admin reactivates suspended vendor. | Done | Done | Done | POST /api/v1/admin/vendors/:id/reinstate. |  | Should Have | 4.11.3
V-18 | Deactivate Vendor | Admin permanently deactivates vendor. | Done | Done | Done | POST /api/v1/admin/vendors/:id/deactivate. |  | Should Have | 4.11.3
Public Vendor Discovery
V-19 | Public Vendor Listing | Couples browse verified vendors with search/filter. | Done | Done | Done | GET /api/v1/vendors with category, location, search, pagination, sort filters. Frontend /vendors page. |  | Must Have | 3.2.2, US-C-004
V-20 | Vendor Detail Page | Couples view full vendor profile, portfolio, reviews. | Done | Done | Done | GET /api/v1/vendors/:id. Frontend /vendors/[id] page with full profile. |  | Must Have | 3.4.2 UC8
V-21 | Vendor Filtering by Category | Filter vendors by service type (photographer, caterer, etc.). | Done | Done | Done | category query param in public vendor listing API. |  | Must Have | US-C-004
V-22 | Vendor Filtering by Location | Filter vendors by city/area. | Done | Done | Done | location query param in public vendor listing API. |  | Must Have | US-C-004
V-23 | Vendor Filtering by Verification Status | Show only verified vendors to couples. | Done | Done | Done | Public API only returns verified vendors by default. |  | Must Have | US-C-007
V-24 | Save Vendors to Favorites | Couple saves vendors for later comparison. | Not Started | Not Started | Not Started | No favorites/saved vendors implementation. | Build favorites table, API endpoints, and heart/save button in vendor cards. | Could Have | US-C-008

## 3. Real-Time Comms
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Socket.IO Infrastructure
R-01 | Socket.IO Server Setup | WebSocket server with authentication. | Done | Done | Done | createSocketServer in socket-server.ts with cookie-based auth middleware. |  | Must Have | 3.2.6
R-02 | Socket.IO Client Connection | Frontend establishes authenticated WS connection. | Done | Done | Done | socket-client.ts singleton with withCredentials. SocketProvider manages lifecycle. |  | Must Have | 3.2.6
R-03 | Room-based Architecture | Users join/leave rooms for targeted messaging. | Done | Done | Done | Users join user:{id} room on connect. Chat rooms joined/left via hooks. |  | Must Have | 3.2.6
Chat / Messaging
R-04 | Create Conversation | Couple initiates conversation with vendor. | Done | Done | Done | POST /api/v1/conversations with participantId. Frontend starts conversation from vendor detail page. |  | Must Have | 3.2.6, US-C-015
R-05 | List Conversations | User sees all their active conversations. | Done | Done | Done | GET /api/v1/conversations. ChatList component shows conversations. |  | Must Have | 3.2.6
R-06 | Send Text Message | Real-time text message delivery. | Done | Done | Done | chat:send event via Socket.IO. Message persisted in chat_message table. |  | Must Have | 3.2.6
R-07 | Message History | Load previous messages for a conversation. | Done | Done | Done | GET /api/v1/conversations/:id/messages. useChat hook loads on room join. |  | Must Have | 3.2.6
R-08 | Typing Indicators | Show when other user is typing. | Done | Done | Done | chat:typing and chat:stopTyping events. UI shows typing state. |  | Should Have | Scenario 4
R-09 | Read Receipts | Mark messages as read, show double ticks. | Done | Done | Done | chat:markRead event updates isRead. UI shows read status. |  | Should Have | Scenario 4
R-10 | File Attachments in Chat | Send contracts, invoices, images in chat. | Not Started | Not Started | Not Started | No file attachment support in chat messages. | Add file upload endpoint for chat, message type field, file preview in chat UI. | Should Have | US-C-017
Notifications
R-11 | In-App Notifications | Real-time notification delivery to connected users. | Done | Done | Done | notification:new event via Socket.IO. NotificationDropdown shows list. |  | Must Have | 3.2.6
R-12 | Notification REST API | Fetch notifications, mark as read. | Done | Done | Done | GET /api/v1/notifications, PATCH /:id/read, PATCH /read-all. |  | Must Have | 3.2.6
R-13 | Notification Bell/Badge | Visual indicator of unread notifications. | Done | Done | Done | NotificationBell component with unread count badge. |  | Must Have | 3.2.6
R-14 | Push Notifications (Mobile/Browser) | Notifications when app is closed or in background. | Not Started | Not Started | Not Started | Only in-app socket notifications exist. | Integrate Web Push API / Firebase Cloud Messaging for background notifications. | Should Have | US-C-018
R-15 | Email Notifications | Email alerts for critical events (booking, payment). | Not Started | Not Started | Not Started | Email service exists but only for auth flows. | Extend email service for booking confirmations, payment receipts, reminders. | Could Have | 3.2.6
Presence
R-16 | User Online/Offline Status | Show if user is currently online. | Done | Done | Done | presence:update event. PresenceDot component shows green/gray dot. |  | Could Have | 3.2.6

## 4. Budgeting & Expense
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Budget Planning
B-01 | Create Wedding Budget | Couple defines total wedding budget amount. | Not Started | Not Started | Not Started | No budget implementation exists. | Create budget table, POST /api/v1/budgets endpoint, budget creation UI page. | Must Have | 3.2.5, US-C-009
B-02 | Budget Category Allocation | Allocate budget into categories (venue, catering, photo, etc.). | Not Started | Not Started | Not Started | No budget categories implementation. | Create budget_categories table, CRUD API, category allocation UI with sliders/inputs. | Must Have | 3.2.5, US-C-009
B-03 | AI-Suggested Budget Allocation | System suggests category distribution based on total budget and wedding type. | Not Started | Not Started | Not Started | No AI budget suggestion implementation. | Build recommendation logic for budget distribution, API endpoint, suggestion UI. | Should Have | 3.2.5, US-C-010
Expense Tracking
B-04 | Add Expense Entry | Record individual expenses against budget categories. | Not Started | Not Started | Not Started | No expense implementation. | Create expenses table, POST /api/v1/expenses endpoint, expense form UI. | Must Have | 3.2.5, US-C-011
B-05 | Real-Time Budget Totals | Dashboard shows live spending vs allocated amounts. | Not Started | Not Started | Not Started | No budget dashboard. | Build budget summary calculations, real-time update UI with progress bars. | Must Have | 3.2.5, US-C-011
B-06 | Budget Alerts & Limits | Warnings when spending approaches/exceeds category limits. | Not Started | Not Started | Not Started | No alert system for budgets. | Add threshold logic, notification triggers, alert banners in budget UI. | Should Have | 3.2.5, US-C-012
B-07 | Receipt Upload | Attach receipt images to expense entries. | Not Started | Not Started | Not Started | No receipt upload functionality. | Add receipt storage (Supabase), upload API, receipt preview in expense detail. | Could Have | US-C-013
B-08 | Budget Summary Reports | Generate exportable budget reports. | Not Started | Not Started | Not Started | No reporting functionality. | Build report generation API, PDF/CSV export, report view page. | Could Have | US-C-014

## 5. AI Recommendations
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Recommendation Engine
AI-01 | Content-Based Filtering | Recommend vendors using attributes (category, location, price, tags). | Not Started | Not Started | Not Started | No AI/ML implementation. vendor_profiles has category, location, price fields for future use. | Build vendor vectorization, similarity scoring, content-based recommendation API. | Must Have | 3.2.4, 4.6.3
AI-02 | Collaborative Filtering | Recommend vendors based on similar couples' behavior. | Not Started | Not Started | Not Started | No interaction tracking or matrix factorization. | Build user-vendor interaction tracking, matrix factorization model, training pipeline. | Should Have | 3.2.4, 4.6.3
AI-03 | Hybrid Weighted Approach | Combine content + collaborative with adaptive weights based on data maturity. | Not Started | Not Started | Not Started | No hybrid engine. | Implement weighted scoring: 100% content early, shift to 70% collaborative at maturity. | Should Have | 3.2.4, 4.6.3
AI-04 | Cold-Start Handling | Ensure meaningful recommendations with zero interaction data. | Not Started | Not Started | Not Started | No cold-start strategy implemented. | Default to content-based only. Use vendor metadata + couple preferences for initial scoring. | Must Have | 3.2.4, 4.6.3
AI-05 | User Preference Collection | Gather couple preferences (theme, location, budget, style). | Not Started | Not Started | Not Started | No preference collection UI or storage. | Build preference wizard during couple onboarding, store in user_preferences table. | Must Have | 3.2.4
Caching & Performance
AI-06 | Redis Recommendation Cache | Cache computed recommendations for 24h per user. | Not Started | Not Started | Not Started | No Redis setup in project. | Add Redis dependency, cache layer for recommendations, TTL-based invalidation. | Must Have | 4.6.3
AI-07 | Cache Invalidation Rules | Invalidate cache on preference update, new booking, or vendor profile change. | Not Started | Not Started | Not Started | No cache infrastructure. | Implement cache key strategy, event-driven invalidation hooks. | Should Have | 4.6.3
AI-08 | Sub-2-Second Response | Recommendation results within 2 seconds. | Not Started | Not Started | Not Started | No performance benchmarks. | Optimize query paths, pre-compute scores, use Redis for instant retrieval. | Must Have | 3.3.1
Recommendation UI
AI-09 | Recommendation Badges | Highlight top-matched vendors with AI badges. | Not Started | Not Started | Not Started | No recommendation UI elements. | Add badge component, match score display, 'Recommended for You' section. | Should Have | Scenario 5
AI-10 | Personalized Vendor Search | AI-ranked search results based on couple profile. | Not Started | Not Started | Not Started | Current search is basic filter-only. | Integrate AI scoring into vendor search pipeline, re-rank results. | Must Have | Scenario 5, US-C-006

## 6. Booking & Scheduling
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Booking Workflow
BK-01 | Send Booking Request | Couple submits booking request with date and requirements. | Not Started | Not Started | Not Started | No booking implementation. | Create bookings table, POST /api/v1/bookings endpoint, booking request form UI. | Must Have | 3.4.2 UC9, US-C-016
BK-02 | Vendor Reviews Booking | Vendor sees incoming booking requests on dashboard. | Not Started | Not Started | Not Started | No booking list for vendors. | Build vendor bookings list API, incoming requests page, accept/decline UI. | Must Have | 3.4.2 UC9
BK-03 | Accept/Decline Booking | Vendor accepts or declines with optional message. | Not Started | Not Started | Not Started | No booking status workflow. | Add booking status machine (pending/accepted/declined/completed), status update API. | Must Have | 3.4.2 UC9
BK-04 | Booking Status Tracking | Both parties see current booking status. | Not Started | Not Started | Not Started | No booking status UI. | Build booking detail page with status timeline, notifications on status change. | Must Have | 3.4.2 UC9
BK-05 | Booking Confirmation Notification | Notify couple when vendor accepts/declines. | Not Started | Not Started | Not Started | Notification system exists but no booking triggers. | Wire booking status changes to notification service. | Must Have | US-C-018
Scheduling & Calendar
BK-06 | Vendor Availability Calendar | Vendors set available/blocked dates. | Not Started | Not Started | Not Started | No calendar implementation. | Build availability_slots table, calendar API, interactive calendar UI (vendor side). | Should Have | 3.2.2
BK-07 | Date Conflict Detection | Prevent double-booking on same date. | Not Started | Not Started | Not Started | No conflict logic. | Add unique constraint on vendor+date, validation in booking API. | Should Have | 3.2.2
BK-08 | Booking History | List of past and upcoming bookings for both roles. | Not Started | Not Started | Not Started | No booking history. | Build booking list API with status filters, history pages for couple and vendor. | Must Have | US-C-021

## 7. Payment Integration
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Payment Integration
P-01 | Chapa Payment Gateway | Integrate Chapa API for accepting payments. | Not Started | Not Started | Not Started | No payment dependencies or code. | Add Chapa SDK, payment initiation API, webhook handler, payment model. | Must Have | 3.2.7
P-02 | Telebirr Integration | Support Telebirr mobile money payments. | Not Started | Not Started | Not Started | No Telebirr integration. | Research Telebirr API, implement payment adapter, add to checkout flow. | Should Have | 3.2.7
P-03 | CBE Birr Integration | Support CBE Birr payments. | Not Started | Not Started | Not Started | No CBE Birr integration. | Research CBE Birr API, implement payment adapter. | Could Have | 3.2.7
Payment Workflow
P-04 | Advance Deposit Payment | Couple makes deposit to secure booking. | Not Started | Not Started | Not Started | No deposit workflow. | Build deposit flow: initiate -> redirect to gateway -> confirm via webhook -> update booking. | Must Have | 3.2.7, US-C-020
P-05 | Final Payment | Complete remaining payment after service delivery. | Not Started | Not Started | Not Started | No final payment flow. | Build final payment trigger, amount calculation (total - deposit), payment confirmation. | Must Have | 3.2.7
P-06 | Escrow-Style Workflow | Hold funds until service is delivered/confirmed. | Not Started | Not Started | Not Started | No escrow mechanism. | Design escrow state machine, hold/release/refund flows, dispute handling. | Should Have | 3.2.7
P-07 | Payment History | View all transactions linked to bookings. | Not Started | Not Started | Not Started | No payment records. | Build payments table, transaction history API, payment history page. | Must Have | 3.2.7, US-C-021
P-08 | Payment-Expense Linkage | Auto-record payments as expenses in budget. | Not Started | Not Started | Not Started | No budget-payment integration. | Link payment confirmation to expense creation, auto-categorize by vendor type. | Should Have | 3.2.7

## 8. Review & Feedback
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Review Submission
RV-01 | Submit Rating & Review | Couple rates vendor with stars (1-5) and text comment after completed booking. | Not Started | Not Started | Not Started | vendor_profiles has rating and review_count fields but no review submission system. | Create reviews table, POST /api/v1/reviews endpoint, review form UI on completed bookings. | Must Have | 3.2.8, US-C-022
RV-02 | One Review Per Booking | Prevent duplicate reviews for same booking. | Not Started | Not Started | Not Started | No review logic. | Add unique constraint on booking_id in reviews table, check in API. | Must Have | 3.2.8, Scenario 3
RV-03 | Photo Upload with Review | Couple uploads wedding photos as visual feedback. | Not Started | Not Started | Not Started | No review photo upload. | Add review_photos table, image upload to Supabase, photo gallery in review display. | Could Have | US-C-023
Review Management
RV-04 | Vendor Rating Aggregation | Auto-calculate average vendor rating from reviews. | Not Started | Not Started | Not Started | Fields exist in vendor_profiles but no aggregation logic. | Build trigger/service to recalculate avg rating on new review, update vendor record. | Must Have | 3.2.8, Scenario 3
RV-05 | Admin Review Moderation | Admin approves or removes inappropriate reviews. | Not Started | Not Started | Not Started | No review moderation. | Add isApproved field, admin review queue API, moderation UI page. | Must Have | 3.4.2 UC15
RV-06 | Review Display on Vendor Profile | Show approved reviews on public vendor page. | Not Started | Not Started | Not Started | Vendor detail page exists but shows no reviews. | Fetch reviews for vendor, display review cards with stars, text, photos, date. | Must Have | 3.2.8
RV-07 | Review Feeds AI Recommendations | Use review data as signal for collaborative filtering. | Not Started | Not Started | Not Started | No AI integration. | Include review scores in recommendation scoring matrix. | Should Have | 3.2.4, 4.6.3
RV-08 | Vendor Notification on New Review | Notify vendor when they receive a review. | Not Started | Not Started | Not Started | Notification system exists but no review trigger. | Wire review creation to notification service. | Should Have | Scenario 3

## 9. Admin & Analytics
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
User Management
AD-01 | View All Users | Admin sees all registered users (couples, vendors, admins). | In Progress | In Progress | Not Started | Better Auth Admin plugin provides user management API. No custom admin UI. | Build admin users list page with role filter, search, pagination. | Must Have | US-A-001
AD-02 | Suspend/Ban User | Admin suspends or bans accounts violating policies. | In Progress | Done | Not Started | Admin plugin has ban/suspend capabilities. No frontend UI. | Build user action buttons, confirmation dialogs, banned state display. | Must Have | US-A-002
AD-03 | Reactivate User | Admin reactivates suspended accounts after review. | In Progress | Done | Not Started | Admin plugin supports reactivation. No frontend UI. | Add reactivate button in user detail, confirmation flow. | Should Have | US-A-003
AD-04 | Impersonate User Session | Admin views platform as specific user for troubleshooting. | In Progress | Done | Not Started | Admin plugin supports impersonation with audit logging. No UI. | Build impersonation button, session swap UI, exit-impersonation banner. | Could Have | US-A-004
Vendor Verification (Admin)
AD-05 | Vendor Verification Dashboard | Dedicated panel for reviewing vendor applications. | Done | Done | Done | Full implementation: list vendors, view documents, approve/reject/suspend. |  | Must Have | 3.2.3
AD-06 | Document Review Interface | View uploaded vendor documents inline. | Done | Done | Done | Admin vendor detail page shows document list with download links. |  | Must Have | 3.2.3
Analytics & Reporting
AD-07 | Platform Analytics Dashboard | Overview of user counts, vendor stats, booking volume. | Not Started | Not Started | Not Started | No analytics implementation. | Build analytics queries, stats API endpoint, dashboard with charts. | Should Have | 4.6.8
AD-08 | Revenue Reports | Track platform revenue from payments. | Not Started | Not Started | Not Started | No revenue tracking. | Build revenue aggregation queries, report generation, export functionality. | Could Have | 4.6.8
AD-09 | User Activity Reports | Monitor engagement, registration trends. | Not Started | Not Started | Not Started | No activity tracking. | Build activity logging, trend calculations, report UI. | Could Have | 4.6.8
AD-10 | System Health Monitoring | Uptime, response times, error rates. | Not Started | Not Started | Not Started | No monitoring setup. | Integrate monitoring service (e.g., health endpoint exists), build status page. | Should Have | 3.3.2
Content Moderation
AD-11 | Review Moderation Queue | Admin reviews and approves/rejects user reviews. | Not Started | Not Started | Not Started | No review system built yet. | Build with review system: moderation queue, approve/reject actions. | Must Have | 3.4.2 UC15
AD-12 | Content Moderator Role | Assign limited admin privileges to moderators. | Not Started | Not Started | Not Started | Admin plugin supports roles but no moderator distinction in UI. | Add role assignment UI, moderator-specific nav/permissions. | Could Have | 4.11.3

## 10. Couple Planning
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Wedding Project
C-01 | Create Wedding Plan | Initialize wedding with date, location, theme, guest estimate. | Not Started | Not Started | Not Started | No wedding project entity or API. | Create wedding_projects table, CRUD API, wedding plan setup wizard. | Must Have | 3.4.2 UC4, US-C-002
C-02 | Wedding Profile Customization | Set and update wedding preferences at any time. | Not Started | Not Started | Not Started | No preferences UI or storage. | Build preferences page with theme, style, and location fields. | Must Have | US-C-003
C-03 | Wedding Dashboard | Central overview of planning progress. | In Progress | In Progress | In Progress | Couple dashboard exists with placeholder stat cards (Budget, Checklist, Guests show 'ready: false'). | Connect dashboard stats to real data from budget, checklist, and guest list modules. | Must Have | 3.4.1
Checklist & Timeline
C-04 | Wedding Checklist | Pre-built and custom task checklist for planning. | Not Started | Not Started | Not Started | Couple nav has 'Checklist' link but no page or API. | Build checklist_items table, CRUD API, checklist page with categories and deadlines. | Must Have | 1.5.1
C-05 | Task Deadlines & Reminders | Set due dates for checklist items with reminders. | Not Started | Not Started | Not Started | No reminder/scheduling system. | Add due_date field, reminder notification triggers, overdue highlighting. | Should Have | 1.5.1
C-06 | Planning Timeline/Milestones | Visual timeline of key milestones. | Not Started | Not Started | Not Started | No timeline implementation. | Build milestone model, timeline visualization component. | Could Have | 1.5.1
Guest Management
C-07 | Guest List | Manage invited guests with contact details. | Not Started | Not Started | Not Started | Couple nav has 'Guest List' link but no page or API. | Build guests table, CRUD API, guest list page with add/edit/delete. | Must Have | 1.5.1
C-08 | RSVP Tracking | Track guest responses (attending/not attending/pending). | Not Started | Not Started | Not Started | No RSVP system. | Add RSVP status field, guest-facing RSVP page/link, status tracking UI. | Should Have | 1.5.1
C-09 | Guest Count & Seating | Track total guests and optional seating arrangement. | Not Started | Not Started | Not Started | No seating management. | Build seating plan model, table assignment UI. | Could Have | 1.5.1
Discovery & Favorites
C-10 | Vendor Favorites List | Save vendors to compare later. | Not Started | Not Started | Not Started | No favorites implementation. | Build favorites table, toggle API, favorites page, heart icons on vendor cards. | Could Have | US-C-008
C-11 | Vendor Comparison | Side-by-side comparison of saved vendors. | Not Started | Not Started | Not Started | No comparison feature. | Build comparison view with key metrics (price, rating, location) side by side. | Could Have | US-C-005

## 11. Non-Functional
ID | Feature Name | Description | Status | Backend | Frontend | Implementation Notes | Remaining Work | Priority | Doc Reference
Performance
NF-01 | Sub-2-Second Response Time | 95% of requests respond within 1 second. | In Progress | In Progress | In Progress | Basic API responses are fast. No load testing or optimization done. | Add performance monitoring, load testing, optimize slow queries, add caching. | Must Have | 3.3.1
NF-02 | 5000 Concurrent Users | System supports 5000+ concurrent active users. | Not Started | Not Started | Not Started | No load testing or scaling configuration. | Load test with k6/Artillery, configure horizontal scaling, optimize WebSocket capacity. | Should Have | 3.3.1
NF-03 | Recommendation < 800ms | AI recommendations return within 800ms. | Not Started | Not Started | Not Started | No AI system to benchmark. | Will depend on Redis caching strategy once AI engine is built. | Should Have | 3.3.1
Security
NF-04 | HTTPS/TLS Encryption | All client-server communication encrypted. | In Progress | In Progress | In Progress | Development uses HTTP. Production will require TLS setup. | Configure TLS certificates for production deployment. | Must Have | 3.3.3
NF-05 | Data Encryption at Rest | Sensitive fields encrypted in database. | Not Started | Not Started | Not Started | No field-level encryption implemented. | Identify PII fields, implement encryption/decryption layer. | Should Have | 3.3.3, 4.8.5
NF-06 | Input Validation (OWASP) | All API inputs validated against injection. | In Progress | In Progress | In Progress | Some validation in controllers. No comprehensive validation framework. | Add Zod/Joi schema validation on all endpoints, sanitize inputs. | Must Have | 3.3.3
NF-07 | SQL Injection Prevention | Parameterized queries throughout. | Done | Done | Done | Repository layer uses parameterized queries with pg client. |  | Must Have | 3.3.3
Reliability & Availability
NF-08 | 99.5% Monthly Uptime | System available 99.5% of the time. | Not Started | Not Started | Not Started | No uptime monitoring or redundancy. | Configure health checks, auto-restart, monitoring alerts. | Should Have | 3.3.2
NF-09 | Daily Automated Backups | PostgreSQL backup with RPO <= 24 hours. | Not Started | Not Started | Not Started | Neon provides some backup but no custom strategy. | Configure Neon automated backups, verify PITR capability. | Should Have | 3.3.2, 4.8.4
NF-10 | Disaster Recovery (RTO <= 4h) | Recover from critical failures within 4 hours. | Not Started | Not Started | Not Started | No DR plan. | Document recovery procedures, test backup restoration. | Should Have | 3.3.2, 4.8.4
Scalability & Infrastructure
NF-11 | Horizontal Backend Scaling | Backend supports multiple instances. | In Progress | In Progress | Not Started | Stateless Express API supports scaling. Socket.IO needs Redis adapter for multi-instance. | Add Socket.IO Redis adapter, configure load balancer. | Should Have | 3.3.6
NF-12 | Database Indexing & Caching | Efficient queries with proper indexes. | In Progress | In Progress | Not Started | vendor_profiles has btree_gist index. No Redis caching layer. | Add Redis for frequently accessed data, optimize query plans. | Should Have | 3.3.6
NF-13 | Cloud Deployment | Deploy to AWS/GCP/Vercel. | Not Started | Not Started | Not Started | Running locally only. | Configure CI/CD pipeline, deploy backend to cloud, frontend to Vercel. | Should Have | 5.5
Mobile & Accessibility
NF-14 | Flutter Mobile App | Cross-platform mobile application. | Not Started | Not Started | Not Started | No Flutter/mobile codebase. | Initialize Flutter project, implement core screens, connect to same backend API. | Should Have | 1.11
NF-15 | Responsive Web UI | Works on mobile browsers and tablets. | In Progress | Done | In Progress | Tailwind CSS used with responsive classes. Not all pages fully tested on mobile. | Test all pages on mobile viewports, fix responsive issues. | Must Have | 3.3.4
NF-16 | Accessibility Standards | WCAG compliance for core interactions. | Not Started | Not Started | Not Started | No accessibility audit done. | Add ARIA labels, keyboard navigation, screen reader testing. | Should Have | 3.3.4