## Test Plan Overview
TWEDAR - Test Plan Document
AI-Enabled Smart Wedding Planning Platform
HOW TO USE THIS TEST PLAN
1. Each tab contains test cases for a specific test type (Unit, Integration, UAT, etc.).
2. Tests are assigned to either Sura or Hanamariam (see Tester column).
3. Use the DROPDOWN in the 'Result' column to record: Pass / Fail / Not Implemented / Blocked / Skipped.
4. Column D (Expected Result) defines the pass/fail criteria.
5. Use the 'Notes' column to record observations, issues, or deviations.
6. Column K (Prerequisites) shows what must exist before running the test.
7. Tests marked '(Future)' require modules to be implemented first - mark as 'Not Implemented'.
8. Priority column helps decide execution order (Must Have first).
9. Auth tests (Unit - Auth sheet) must be completed by May 2.
⚠️ URGENT: Auth tests must be completed by May 2!
TESTER ASSIGNMENT
Sura
Hanamariam
RESULT OPTIONS (Dropdown)
Pass | Test passed - actual matches expected
Fail | Test failed - actual differs from expected
Not Implemented | Feature not yet built - cannot test
Blocked | Cannot test due to dependency or environment issue
Skipped | Intentionally skipped (add justification in Notes)
TEST SUMMARY BY SHEET
Test Type | Tester | Total | High Priority | Not Tested | Deadline
Unit - Auth | Sura | 23 | 22 | 23 | May 2
Unit - Vendor | Sura | 24 | 23 | 24 | May 10
Unit - Admin | Sura | 9 | 7 | 9 | May 10
Unit - Realtime | Sura | 18 | 15 | 18 | May 10
Unit - Budget (Future) | Hanamariam | 7 | 6 | 7 | May 10
Unit - Booking (Future) | Hanamariam | 7 | 6 | 7 | May 10
Unit - Payment (Future) | Hanamariam | 5 | 5 | 5 | May 10
Unit - Review (Future) | Hanamariam | 7 | 7 | 7 | May 10
Integration Tests | Sura | 13 | 10 | 13 | May 10
User Acceptance (UAT) | Hanamariam | 20 | 19 | 20 | May 10
Performance Tests | Hanamariam | 10 | 2 | 10 | May 10
Security Tests | Sura | 20 | 16 | 20 | May 10
TOTAL |  | 163 |  | 163
PER-TESTER SUMMARY
Tester |  | Sheets Assigned | Total Tests
Sura |  | 6 | 107
Hanamariam |  | 6 | 56
TEST ENVIRONMENT
Backend: | Node.js + Express + TypeScript (localhost:5000)
Frontend: | Next.js 16 + React 19 (localhost:3000)
Database: | PostgreSQL on Supabase
Auth: | Better Auth with Organization + Admin plugins
Realtime: | Socket.IO (same backend server)
Storage: | Supabase (vendor documents)
Testing Type: | Manual Testing
Load Testing: | k6 or Artillery (performance)
PROJECT INFO
Project: | Twedar - AI-Enabled Smart Wedding Planning Platform
Testers: | Sura (Auth, Vendor, Admin, Realtime, Integration, Security) ¦ Hanamariam (Budget, Booking, Payment, Review, UAT, Performance)
Generated: | May 2026
Total Test Cases: | 163
Current Pass Rate: | 0% (No tests executed)

## Unit - Auth
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Authentication - Registration
UT-01 | Register with valid credentials | 1. Send POST /api/auth/sign-up with valid email, password, accountType='couple' 2. Verify response status 3. Check database for new user record | 201 Created. User record exists with hashed password, emailVerified=false, role='couple'. | Sura |  |  | Unit | Auth | Must Have | Database connection, email service mock | 3.2.1
UT-02 | Register with duplicate email | 1. Create user with email X 2. Attempt POST /api/auth/sign-up with same email X | 409 Conflict with error message 'Email already exists'. | Sura |  |  | Unit | Auth | Must Have | Existing user in database | 3.2.1
UT-03 | Register with missing email | 1. Send POST /api/auth/sign-up without email field | 400 Bad Request with validation error for email field. | Sura |  |  | Unit | Auth | Must Have | None | 3.2.1
UT-04 | Register with weak password | 1. Send POST /api/auth/sign-up with password '123' | 400 Bad Request with password complexity error. | Sura |  |  | Unit | Auth | Must Have | None | 3.2.1
UT-05 | Register with invalid role | 1. Send POST /api/auth/sign-up with accountType='superadmin' | 400 Bad Request. Only 'couple' and 'vendor' allowed at registration. | Sura |  |  | Unit | Auth | Must Have | None | 3.2.1
UT-06 | Vendor registration creates organization | 1. Register with accountType='vendor' 2. Check organization table | User created with role='vendor'. Organization auto-created with user as owner. | Sura |  |  | Unit | Auth | Must Have | Database connection | 4.11.2
Authentication - Login
UT-07 | Login with correct credentials | 1. Register and verify user 2. POST /api/auth/sign-in with correct email/password | 200 OK. Set-Cookie header with httpOnly session cookie. Response contains user data. | Sura |  |  | Unit | Auth | Must Have | Verified user in database | 3.4.2 UC2
UT-08 | Login with wrong password | 1. POST /api/auth/sign-in with valid email but wrong password | 401 Unauthorized. No cookie set. | Sura |  |  | Unit | Auth | Must Have | Existing user | 3.4.2 UC2
UT-09 | Login with non-existent email | 1. POST /api/auth/sign-in with unregistered email | 401 Unauthorized with generic error (no user enumeration). | Sura |  |  | Unit | Auth | Must Have | None | 3.4.2 UC2
UT-10 | Login with unverified email | 1. Register user (don't verify) 2. Attempt login | Error response indicating email verification required. | Sura |  |  | Unit | Auth | Must Have | Unverified user | 3.2.1
UT-11 | Login with banned account | 1. Ban user via admin 2. Attempt login | 401/403 with message indicating account is banned. | Sura |  |  | Unit | Auth | Must Have | Banned user record | 4.11.3
Authentication - Email Verification
UT-12 | Verify email with valid token | 1. Register user (generates verification token) 2. GET /api/auth/verify?token=<valid_token> | 200 OK. User emailVerified field updated to true. | Sura |  |  | Unit | Auth | Must Have | User with pending verification | 3.2.1
UT-13 | Verify email with expired token | 1. Use an expired/invalid verification token | 400 Bad Request with 'Invalid or expired token' error. | Sura |  |  | Unit | Auth | Must Have | Expired token | 3.2.1
UT-14 | Verify already verified email | 1. Verify email 2. Use same token again | Already verified or token consumed - no error but no state change. | Sura |  |  | Unit | Auth | Should Have | Verified user | 3.2.1
Authentication - Password Reset
UT-15 | Request password reset for valid email | 1. POST /api/auth/forgot-password with registered email | 200 OK. Reset email sent with valid token link. | Sura |  |  | Unit | Auth | Must Have | Verified user, email mock | 3.2.1
UT-16 | Request password reset for non-existent email | 1. POST /api/auth/forgot-password with unregistered email | 200 OK (no user enumeration). No email sent. | Sura |  |  | Unit | Auth | Must Have | Email mock | 3.2.1
UT-17 | Reset password with valid token | 1. Request reset 2. POST /api/auth/reset-password with valid token + new password | 200 OK. Password hash updated. Old password no longer works. | Sura |  |  | Unit | Auth | Must Have | Valid reset token | 3.2.1
UT-18 | Reset password with expired token | 1. Use an expired reset token | 400 Bad Request with 'Token expired' error. | Sura |  |  | Unit | Auth | Must Have | Expired token | 3.2.1
Authentication - Session & Middleware
UT-19 | Access protected route with valid session | 1. Login (get cookie) 2. GET /api/v1/vendor/profile with cookie | 200 OK. Request passes through requireAuth middleware. | Sura |  |  | Unit | Auth | Must Have | Authenticated session | 4.11.1
UT-20 | Access protected route without session | 1. GET /api/v1/vendor/profile without cookie | 401 Unauthorized. | Sura |  |  | Unit | Auth | Must Have | None | 4.11.1
UT-21 | Access vendor route as couple | 1. Login as couple 2. GET /api/v1/vendor/profile | 403 Forbidden. Role mismatch. | Sura |  |  | Unit | Auth | Must Have | Couple session | 4.11.4
UT-22 | Access admin route as vendor | 1. Login as vendor 2. GET /api/v1/admin/vendors | 403 Forbidden. | Sura |  |  | Unit | Auth | Must Have | Vendor session | 4.11.4
UT-23 | Session cookie properties | 1. Login 2. Inspect Set-Cookie header | Cookie is httpOnly, SameSite=lax, path=/. Secure flag in production. | Sura |  |  | Unit | Auth | Must Have | None | 4.11.1

## Unit - Vendor
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Vendor Profile CRUD
UT-24 | Create vendor profile - valid data | 1. Login as vendor 2. POST /api/v1/vendor/profile with business_name, category, description, location | 201 Created. Profile record in database with status='draft'. | Sura |  |  | Unit | Vendor | Must Have | Authenticated vendor | 3.2.2
UT-25 | Create vendor profile - duplicate | 1. Vendor already has profile 2. POST /api/v1/vendor/profile again | 409 Conflict. Only one profile per vendor. | Sura |  |  | Unit | Vendor | Must Have | Vendor with existing profile | 3.2.2
UT-26 | Update vendor profile | 1. PATCH /api/v1/vendor/profile with partial fields (e.g., description only) | 200 OK. Only specified fields updated; others unchanged. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.2
UT-27 | Get own vendor profile | 1. GET /api/v1/vendor/profile as authenticated vendor | 200 OK. Returns full profile with all fields including status. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.2
UT-28 | Get profile as non-vendor | 1. Login as couple 2. GET /api/v1/vendor/profile | 403 Forbidden. | Sura |  |  | Unit | Vendor | Must Have | Couple session | 4.11.4
UT-29 | Update profile with location coordinates | 1. PATCH /api/v1/vendor/profile with latitude, longitude | 200 OK. Geo coordinates stored correctly. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.2
UT-30 | Update profile with price range | 1. PATCH with price_range_min=5000, price_range_max=50000 | 200 OK. Price range stored and retrievable. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.2
Vendor Documents
UT-31 | Upload document - valid file | 1. POST /api/v1/vendor/documents with PDF/image file and document_type | 201 Created. File uploaded to Supabase. Document record in DB with URL. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile, Supabase mock | 3.2.3
UT-32 | Upload document - invalid type | 1. POST /api/v1/vendor/documents with .exe file | 400 Bad Request. Unsupported file type. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.3
UT-33 | Upload document - oversized file | 1. POST /api/v1/vendor/documents with file > max size limit | 413 Payload Too Large. | Sura |  |  | Unit | Vendor | Must Have | Vendor with profile | 3.2.3
UT-34 | Delete own document | 1. DELETE /api/v1/vendor/documents/:id for own document | 200 OK. File removed from Supabase. DB record deleted. | Sura |  |  | Unit | Vendor | Must Have | Vendor with uploaded document | 3.2.3
UT-35 | Delete another vendor's document | 1. DELETE /api/v1/vendor/documents/:id for another vendor's doc | 403 or 404. Cannot delete others' documents. | Sura |  |  | Unit | Vendor | Must Have | Two vendors with documents | 3.2.3
Vendor Verification Workflow
UT-36 | Submit profile for verification | 1. POST /api/v1/vendor/profile/submit when status='draft' and documents uploaded | 200 OK. Status transitions to 'pending_verification'. | Sura |  |  | Unit | Vendor | Must Have | Draft profile with documents | 3.2.3
UT-37 | Submit without documents | 1. POST /api/v1/vendor/profile/submit with no documents uploaded | 400 Bad Request. Documents required for verification. | Sura |  |  | Unit | Vendor | Must Have | Draft profile, no documents | 3.2.3
UT-38 | Submit already pending profile | 1. Profile already in 'pending_verification' 2. POST /api/v1/vendor/profile/submit again | 400 Bad Request. Invalid status transition. | Sura |  |  | Unit | Vendor | Must Have | Pending profile | 3.2.3
UT-39 | Resubmit after rejection | 1. Profile in 'rejected' status 2. Update profile 3. POST /api/v1/vendor/profile/submit | 200 OK. Status transitions from 'rejected' back to 'pending_verification'. | Sura |  |  | Unit | Vendor | Should Have | Rejected profile | 3.2.3
UT-40 | Status machine - invalid transitions | 1. Attempt transition from 'draft' directly to 'verified' | Error thrown. Only valid transitions allowed (draft->pending, pending->verified/rejected). | Sura |  |  | Unit | Vendor | Must Have | Draft profile | 3.2.3
Public Vendor Listing
UT-41 | List vendors - no filters | 1. GET /api/v1/vendors without query params | 200 OK. Returns paginated list of verified vendors only. | Sura |  |  | Unit | Vendor | Must Have | Verified vendors in DB | US-C-004
UT-42 | List vendors - category filter | 1. GET /api/v1/vendors?category=photographer | 200 OK. Only vendors with category='photographer' returned. | Sura |  |  | Unit | Vendor | Must Have | Vendors with varied categories | US-C-004
UT-43 | List vendors - location filter | 1. GET /api/v1/vendors?location=Addis Ababa | 200 OK. Only vendors in specified location returned. | Sura |  |  | Unit | Vendor | Must Have | Vendors with varied locations | US-C-004
UT-44 | List vendors - search keyword | 1. GET /api/v1/vendors?search=wedding photography | 200 OK. Vendors matching search in name/description returned. | Sura |  |  | Unit | Vendor | Must Have | Vendors with varied descriptions | US-C-004
UT-45 | List vendors - pagination | 1. GET /api/v1/vendors?page=2&limit=5 | 200 OK. Returns page 2 with max 5 items. Pagination metadata included. | Sura |  |  | Unit | Vendor | Must Have | 10+ verified vendors | US-C-004
UT-46 | Get vendor detail - valid ID | 1. GET /api/v1/vendors/:id for verified vendor | 200 OK. Full profile with all public fields. | Sura |  |  | Unit | Vendor | Must Have | Verified vendor | 3.4.2 UC8
UT-47 | Get vendor detail - unverified vendor | 1. GET /api/v1/vendors/:id for unverified vendor | 404 Not Found. Unverified vendors not publicly accessible. | Sura |  |  | Unit | Vendor | Must Have | Unverified vendor | US-C-007

## Unit - Admin
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Admin Vendor Management
UT-48 | Admin list all vendors | 1. Login as admin 2. GET /api/v1/admin/vendors | 200 OK. Returns all vendors regardless of status with status field. | Sura |  |  | Unit | Admin | Must Have | Admin session, vendors in DB | US-A-005
UT-49 | Non-admin access admin vendors | 1. Login as couple 2. GET /api/v1/admin/vendors | 403 Forbidden. | Sura |  |  | Unit | Admin | Must Have | Couple session | 4.11.4
UT-50 | Approve pending vendor | 1. POST /api/v1/admin/vendors/:id/approve for pending vendor | 200 OK. Vendor status changes to 'verified'. Vendor appears in public listing. | Sura |  |  | Unit | Admin | Must Have | Admin session, pending vendor | 3.4.2 UC14
UT-51 | Approve non-pending vendor | 1. POST /api/v1/admin/vendors/:id/approve for already verified vendor | 400 Bad Request. Invalid status transition. | Sura |  |  | Unit | Admin | Must Have | Admin session, verified vendor | 3.4.2 UC14
UT-52 | Reject vendor with reason | 1. POST /api/v1/admin/vendors/:id/reject with body { reason: 'Invalid license' } | 200 OK. Status changes to 'rejected'. Rejection reason stored. | Sura |  |  | Unit | Admin | Must Have | Admin session, pending vendor | 3.4.2 UC14
UT-53 | Reject vendor without reason | 1. POST /api/v1/admin/vendors/:id/reject without reason field | 400 Bad Request. Reason is required. | Sura |  |  | Unit | Admin | Must Have | Admin session, pending vendor | 3.4.2 UC14
UT-54 | Suspend verified vendor | 1. POST /api/v1/admin/vendors/:id/suspend for verified vendor | 200 OK. Status changes to 'suspended'. Vendor removed from public listing. | Sura |  |  | Unit | Admin | Must Have | Admin session, verified vendor | 4.11.3
UT-55 | Reinstate suspended vendor | 1. POST /api/v1/admin/vendors/:id/reinstate for suspended vendor | 200 OK. Status changes back to 'verified'. Vendor re-appears in public listing. | Sura |  |  | Unit | Admin | Should Have | Admin session, suspended vendor | 4.11.3
UT-56 | Deactivate vendor | 1. POST /api/v1/admin/vendors/:id/deactivate | 200 OK. Vendor permanently deactivated. | Sura |  |  | Unit | Admin | Should Have | Admin session, verified vendor | 4.11.3

## Unit - Realtime
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Conversation Management
UT-57 | Create conversation - valid | 1. POST /api/v1/conversations with { participantId: vendor_user_id } | 201 Created. Conversation record with both participant IDs. Returns conversation object. | Sura |  |  | Unit | Realtime | Must Have | Authenticated couple, existing vendor | 3.2.6
UT-58 | Create duplicate conversation | 1. POST /api/v1/conversations with same participantId as existing conversation | 200 OK. Returns existing conversation (no duplicate created). | Sura |  |  | Unit | Realtime | Must Have | Existing conversation pair | 3.2.6
UT-59 | Create conversation with self | 1. POST /api/v1/conversations with own user ID as participantId | 400 Bad Request. Cannot create conversation with self. | Sura |  |  | Unit | Realtime | Must Have | Authenticated user | 3.2.6
UT-60 | List conversations | 1. GET /api/v1/conversations as authenticated user | 200 OK. Returns only conversations where user is a participant. Sorted by last message. | Sura |  |  | Unit | Realtime | Must Have | User with conversations | 3.2.6
UT-61 | Get messages for own conversation | 1. GET /api/v1/conversations/:id/messages for user's conversation | 200 OK. Returns messages in chronological order. | Sura |  |  | Unit | Realtime | Must Have | Conversation with messages | 3.2.6
UT-62 | Get messages for others' conversation | 1. GET /api/v1/conversations/:id/messages for conversation user is NOT part of | 403 Forbidden. | Sura |  |  | Unit | Realtime | Must Have | Other users' conversation | 3.2.6
Socket.IO - Connection & Auth
UT-63 | Socket connect with valid session | 1. Connect to Socket.IO server with valid session cookie | Connection accepted. User joins user:{userId} room. | Sura |  |  | Unit | Realtime | Must Have | Valid session cookie | 3.2.6
UT-64 | Socket connect without session | 1. Connect to Socket.IO server without cookie | Connection rejected with authentication error. | Sura |  |  | Unit | Realtime | Must Have | None | 3.2.6
UT-65 | Socket disconnect cleanup | 1. Connect 2. Disconnect 3. Verify room membership removed | User removed from all rooms. Presence updated to offline. | Sura |  |  | Unit | Realtime | Must Have | Connected socket | 3.2.6
Socket.IO - Chat Events
UT-66 | Send message (chat:send) | 1. Emit chat:send with { conversationId, content } 2. Check database and receiver | Message saved to chat_message table. Receiver gets chat:newMessage event. | Sura |  |  | Unit | Realtime | Must Have | Two connected users in conversation | 3.2.6
UT-67 | Send message to invalid conversation | 1. Emit chat:send with non-existent conversationId | Error callback. Message not saved. | Sura |  |  | Unit | Realtime | Must Have | Connected user | 3.2.6
UT-68 | Typing indicator (chat:typing) | 1. Emit chat:typing with { conversationId } 2. Check other participant receives event | Other participant receives chat:userTyping event. | Sura |  |  | Unit | Realtime | Should Have | Two connected users in conversation | Scenario 4
UT-69 | Stop typing (chat:stopTyping) | 1. Emit chat:stopTyping with { conversationId } | Other participant receives chat:userStoppedTyping event. | Sura |  |  | Unit | Realtime | Should Have | Two connected users in conversation | Scenario 4
UT-70 | Mark as read (chat:markRead) | 1. Emit chat:markRead with { conversationId, messageId } 2. Check database update | Message isRead=true in DB. Sender receives chat:messageRead event. | Sura |  |  | Unit | Realtime | Should Have | Unread message in conversation | Scenario 4
Notifications
UT-71 | Get notifications - authenticated | 1. GET /api/v1/notifications | 200 OK. Returns user's notifications ordered by createdAt desc. | Sura |  |  | Unit | Realtime | Must Have | User with notifications | 3.2.6
UT-72 | Mark single notification read | 1. PATCH /api/v1/notifications/:id/read | 200 OK. Notification isRead updated to true. | Sura |  |  | Unit | Realtime | Must Have | Unread notification | 3.2.6
UT-73 | Mark all notifications read | 1. PATCH /api/v1/notifications/read-all | 200 OK. All user's notifications marked as read. | Sura |  |  | Unit | Realtime | Must Have | Multiple unread notifications | 3.2.6
UT-74 | Real-time notification delivery | 1. Trigger notification (e.g., new message) 2. Check connected user's socket receives event | notification:new event emitted to user:{targetId} room with notification data. | Sura |  |  | Unit | Realtime | Must Have | Connected target user | 3.2.6

## Unit - Budget
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Budget CRUD (Future Implementation)
UT-75 | Create budget | 1. POST /api/v1/budgets with { totalAmount, currency } | 201 Created. Budget record with status 'active'. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | 3.2.5
UT-76 | Create duplicate budget | 1. Couple already has active budget 2. POST /api/v1/budgets again | 409 Conflict. One active budget per couple. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | 3.2.5
UT-77 | Add category to budget | 1. POST /api/v1/budgets/:id/categories with { name, allocatedAmount } | 201 Created. Category linked to budget. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | US-C-009
UT-78 | Category allocation exceeds total | 1. Add categories that sum > budget total | 400 Bad Request. Total allocations cannot exceed budget. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | 3.2.5
UT-79 | Add expense to category | 1. POST /api/v1/expenses with { categoryId, amount, description } | 201 Created. Expense linked to category. Budget totals recalculated. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | US-C-011
UT-80 | Budget alert at 80% threshold | 1. Add expenses totaling 80%+ of category allocation | Alert notification triggered for approaching limit. | Hanamariam |  |  | Unit | Budget | Should Have | Budget module implemented | US-C-012
UT-81 | Budget summary calculation | 1. GET /api/v1/budgets/:id/summary | 200 OK. Correct totals: spent, remaining, per-category breakdown. | Hanamariam |  |  | Unit | Budget | Must Have | Budget module implemented | US-C-011

## Unit - Booking
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Booking Workflow (Future Implementation)
UT-82 | Create booking request | 1. POST /api/v1/bookings with { vendorId, date, requirements } | 201 Created. Booking with status 'pending'. Vendor notified. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | 3.4.2 UC9
UT-83 | Book unverified vendor | 1. POST /api/v1/bookings with unverified vendorId | 400 Bad Request. Can only book verified vendors. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | 3.4.2 UC9
UT-84 | Vendor accepts booking | 1. PATCH /api/v1/bookings/:id/accept as vendor | 200 OK. Status -> 'accepted'. Couple notified. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | 3.4.2 UC9
UT-85 | Vendor declines booking | 1. PATCH /api/v1/bookings/:id/decline with { reason } | 200 OK. Status -> 'declined'. Couple notified with reason. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | 3.4.2 UC9
UT-86 | Double booking prevention | 1. Vendor has accepted booking for date X 2. Another couple books same vendor for date X | 409 Conflict. Vendor unavailable on that date. | Hanamariam |  |  | Unit | Booking | Should Have | Booking module implemented | 3.2.2
UT-87 | Complete booking | 1. PATCH /api/v1/bookings/:id/complete | 200 OK. Status -> 'completed'. Review now allowed. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | 3.4.2 UC9
UT-88 | Booking history for couple | 1. GET /api/v1/bookings as couple | 200 OK. Returns all bookings for this couple with statuses. | Hanamariam |  |  | Unit | Booking | Must Have | Booking module implemented | US-C-021

## Unit - Payment
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Payment Processing (Future Implementation)
UT-89 | Initiate Chapa payment | 1. POST /api/v1/payments/initiate with { bookingId, amount } | 200 OK. Returns Chapa checkout URL. Payment record with status 'pending'. | Hanamariam |  |  | Unit | Payment | Must Have | Payment module implemented, Chapa mock | 3.2.7
UT-90 | Payment for non-accepted booking | 1. POST /api/v1/payments/initiate for pending/declined booking | 400 Bad Request. Payment only allowed for accepted bookings. | Hanamariam |  |  | Unit | Payment | Must Have | Payment module implemented | 3.2.7
UT-91 | Chapa webhook - success | 1. POST /api/v1/payments/webhook with valid Chapa signature and success payload | 200 OK. Payment status -> 'completed'. Booking updated. | Hanamariam |  |  | Unit | Payment | Must Have | Payment module implemented, valid webhook | 3.2.7
UT-92 | Chapa webhook - invalid signature | 1. POST /api/v1/payments/webhook with tampered signature | 401 Unauthorized. Payment unchanged. | Hanamariam |  |  | Unit | Payment | Must Have | Payment module implemented | 3.2.7
UT-93 | Payment history | 1. GET /api/v1/payments as authenticated user | 200 OK. Returns user's payment transactions with booking references. | Hanamariam |  |  | Unit | Payment | Must Have | Payment module implemented | US-C-021

## Unit - Review
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Review System (Future Implementation)
UT-94 | Submit review for completed booking | 1. POST /api/v1/reviews with { bookingId, rating: 5, comment: 'Great!' } | 201 Created. Review saved with isApproved=false. Vendor notified. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented, completed booking | 3.2.8
UT-95 | Submit review for non-completed booking | 1. POST /api/v1/reviews for booking with status != 'completed' | 400 Bad Request. Reviews only for completed bookings. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | 3.2.8
UT-96 | Submit duplicate review | 1. Review already exists for booking 2. POST /api/v1/reviews for same booking | 409 Conflict. One review per booking. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | Scenario 3
UT-97 | Rating out of range | 1. POST /api/v1/reviews with rating=6 or rating=0 | 400 Bad Request. Rating must be 1-5. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | 3.2.8
UT-98 | Vendor rating aggregation | 1. Submit multiple reviews for same vendor 2. Check vendor avg_rating | Average correctly calculated. review_count incremented. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | Scenario 3
UT-99 | Admin approve review | 1. PATCH /api/v1/admin/reviews/:id/approve | 200 OK. isApproved=true. Review visible on public vendor profile. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | 3.4.2 UC15
UT-100 | Admin reject review | 1. PATCH /api/v1/admin/reviews/:id/reject with { reason } | 200 OK. Review removed or hidden from public view. | Hanamariam |  |  | Unit | Review | Must Have | Review module implemented | 3.4.2 UC15

## Integration
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
End-to-End User Flows
IT-01 | Full couple registration flow | 1. Register couple 2. Verify email via token 3. Login 4. Access /dashboard 5. Verify session cookie | Complete flow works. User ends up authenticated with couple dashboard access. | Sura |  |  | Integration | Auth + Frontend | Must Have | Clean database, email mock | Scenario 1
IT-02 | Full vendor onboarding flow | 1. Register vendor 2. Verify email 3. Login 4. Create profile 5. Upload documents 6. Submit for verification 7. Admin approves 8. Vendor appears in public listing | Complete lifecycle from registration to public visibility. | Sura |  |  | Integration | Auth + Vendor + Admin | Must Have | Clean database, admin account | Scenario 1, Fig 9
IT-03 | Vendor rejection and resubmission | 1. Vendor submits 2. Admin rejects with reason 3. Vendor sees reason 4. Vendor updates and resubmits 5. Admin approves | Rejection reason visible. Resubmission transitions correctly. | Sura |  |  | Integration | Vendor + Admin | Should Have | Pending vendor, admin account | US-V-004
IT-04 | Couple discovers and contacts vendor | 1. Couple searches vendors 2. Filters by category 3. Views vendor detail 4. Starts conversation 5. Sends message 6. Vendor receives message | Search to chat flow works end-to-end. | Sura |  |  | Integration | Vendor + Realtime | Must Have | Verified vendor, couple account | Scenario 2
IT-05 | Real-time chat exchange | 1. Couple sends message 2. Vendor receives in real-time 3. Vendor replies 4. Couple receives reply 5. Read receipts update | Bidirectional real-time messaging with persistence and receipts. | Sura |  |  | Integration | Realtime | Must Have | Two connected users, existing conversation | Scenario 4
IT-06 | Notification lifecycle | 1. Action triggers notification 2. User receives in real-time 3. User marks as read 4. Notification status persists | Notifications created, delivered, and persisted correctly. | Sura |  |  | Integration | Realtime | Must Have | Connected users | 3.2.6
End-to-End Booking Flow (Future)
IT-07 | Complete booking lifecycle | 1. Couple books vendor 2. Vendor accepts 3. Couple pays 4. Service delivered 5. Booking marked complete 6. Couple reviews vendor 7. Rating updates | Full booking-to-review cycle with payment. | Sura |  |  | Integration | Booking + Payment + Review | Must Have | All modules implemented | Scenario 2, 3
IT-08 | Budget-payment integration | 1. Create budget 2. Make payment for booking 3. Payment auto-added as expense 4. Budget totals reflect payment | Payment automatically appears in budget tracking. | Sura |  |  | Integration | Payment + Budget | Should Have | Payment + Budget modules implemented | 3.2.7
IT-09 | AI recommendation with interaction data | 1. Couple books vendor A 2. Couple reviews vendor A 3. Request recommendations 4. Similar vendors ranked higher | Collaborative filtering incorporates booking/review history. | Sura |  |  | Integration | AI + Booking + Review | Should Have | AI + Booking + Review modules implemented | Scenario 5
Cross-Role Security
IT-10 | Couple cannot access vendor endpoints | 1. Login as couple 2. Attempt all /api/v1/vendor/* endpoints | All return 403 Forbidden. | Sura |  |  | Integration | Auth | Must Have | Couple account | 4.11.4
IT-11 | Vendor cannot access admin endpoints | 1. Login as vendor 2. Attempt all /api/v1/admin/* endpoints | All return 403 Forbidden. | Sura |  |  | Integration | Auth | Must Have | Vendor account | 4.11.4
IT-12 | Couple cannot access other couple's data | 1. Login as couple A 2. Attempt to read couple B's conversations/budget | 403 or 404. No cross-user data leakage. | Sura |  |  | Integration | Auth + Realtime | Must Have | Two couple accounts | 3.3.3
IT-13 | Vendor cannot read other vendor's documents | 1. Login as vendor A 2. Attempt to access vendor B's documents | 403 or 404. | Sura |  |  | Integration | Auth + Vendor | Must Have | Two vendor accounts | 3.3.3

## UAT
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
UAT - Couple Experience
UAT-01 | Couple registration to dashboard | 1. Open registration page 2. Fill form (name, email, password, role=couple) 3. Submit 4. Check email for verification link 5. Click link 6. Login 7. Verify dashboard loads with nav items | Smooth registration, verification email arrives, dashboard loads with Budget/Checklist/Guests/Vendors/Messages nav. | Hanamariam |  |  | UAT | Auth + UI | Must Have | Running frontend + backend | Scenario 1
UAT-02 | Google social login | 1. Click 'Continue with Google' on login page 2. Complete Google OAuth 3. Verify redirected to couple dashboard | OAuth flow completes. User created as couple. Dashboard loads. | Hanamariam |  |  | UAT | Auth + UI | Must Have | Google OAuth configured | 3.2.1
UAT-03 | Browse vendor directory | 1. Navigate to 'Find Vendors' 2. See vendor cards grid 3. Use category filter 4. Use location filter 5. Use search bar 6. Verify results update | Filters work correctly. Only verified vendors shown. Cards display name, category, rating, location. | Hanamariam |  |  | UAT | Vendor + UI | Must Have | Verified vendors in DB | US-C-004
UAT-04 | View vendor detail page | 1. Click on vendor card 2. View full profile page 3. See business info, portfolio, pricing, location map | All vendor information displayed clearly. Map shows correct location. Pricing visible. | Hanamariam |  |  | UAT | Vendor + UI | Must Have | Verified vendor with complete profile | 3.4.2 UC8
UAT-05 | Start and use chat | 1. Click 'Message' on vendor profile 2. Type message 3. Send 4. Verify message appears 5. Receive vendor reply 6. See typing indicator 7. See read receipts | Chat is real-time. Messages persist on page refresh. Typing/read indicators work. | Hanamariam |  |  | UAT | Realtime + UI | Must Have | Couple + vendor accounts, both online | Scenario 4
UAT-06 | Receive notifications | 1. Vendor sends message 2. Check notification bell shows badge 3. Click bell 4. See notification dropdown 5. Click notification 6. Mark as read | Badge count updates in real-time. Dropdown shows notification details. Navigation works. | Hanamariam |  |  | UAT | Realtime + UI | Must Have | Connected couple, incoming message | 3.2.6
UAT-07 | Budget management (future) | 1. Navigate to Budget 2. Set total budget 3. Add categories 4. Add expenses 5. View summary with progress bars 6. Receive alert on over-budget | Intuitive budget creation. Real-time totals. Clear visual progress. | Hanamariam |  |  | UAT | Budget + UI | Must Have | Budget module implemented | US-C-009
UAT-08 | Booking flow (future) | 1. Click 'Book' on vendor profile 2. Select date 3. Add requirements 4. Submit request 5. Receive acceptance notification 6. Make payment 7. View booking status | Booking form is clear. Status updates visible. Payment flow smooth. | Hanamariam |  |  | UAT | Booking + Payment + UI | Must Have | Booking + Payment modules implemented | 3.4.2 UC9
UAT-09 | Leave review (future) | 1. Go to completed bookings 2. Click 'Leave Review' 3. Select star rating 4. Write comment 5. Submit 6. See confirmation | Review form intuitive. Stars clickable. Confirmation shown. | Hanamariam |  |  | UAT | Review + UI | Must Have | Review module implemented, completed booking | US-C-022
UAT-10 | AI recommendations (future) | 1. Set preferences during onboarding 2. Navigate to vendor discovery 3. See 'Recommended for You' section 4. Verify suggestions match preferences | Recommendations relevant to stated preferences. AI badges visible on matched vendors. | Hanamariam |  |  | UAT | AI + UI | Must Have | AI module implemented | US-C-006
UAT - Vendor Experience
UAT-11 | Vendor registration and setup | 1. Register as vendor 2. Verify email 3. Login 4. Complete profile setup wizard (name, category, description, pricing, location) 5. Verify all saved | Setup wizard intuitive. All fields save correctly. Map picker works. | Hanamariam |  |  | UAT | Auth + Vendor + UI | Must Have | Running frontend + backend | US-V-001
UAT-12 | Upload verification documents | 1. Navigate to Documents section 2. Upload business license (PDF) 3. Upload ID (image) 4. See uploaded files listed 5. Delete one and re-upload | Upload progress shown. Files listed with names. Delete works. | Hanamariam |  |  | UAT | Vendor + UI | Must Have | Vendor with profile | US-V-002
UAT-13 | Submit for verification | 1. After uploading docs 2. Click 'Submit for Verification' 3. See status banner change to 'Pending' 4. Wait for admin decision 5. See approved/rejected status | Clear status indication throughout. Rejection shows reason. | Hanamariam |  |  | UAT | Vendor + UI | Must Have | Vendor with profile + docs | 3.2.3
UAT-14 | Vendor messaging | 1. Login as vendor 2. Navigate to Messages 3. See conversation list 4. Open conversation 5. Reply to couple 6. Send with typing indicator | Messages page shows all conversations. Real-time delivery works both ways. | Hanamariam |  |  | UAT | Realtime + UI | Must Have | Vendor with existing conversations | Scenario 4
UAT-15 | Vendor manages bookings (future) | 1. See incoming booking requests 2. Review request details 3. Accept one 4. Decline another with reason 5. View booking calendar | Booking requests clearly displayed. Accept/decline smooth. Calendar accurate. | Hanamariam |  |  | UAT | Booking + UI | Must Have | Booking module implemented | 3.4.2 UC9
UAT - Admin Experience
UAT-16 | Admin reviews vendor applications | 1. Login as admin 2. Navigate to Vendor Management 3. See list of pending vendors 4. Click one to view details 5. View uploaded documents 6. Approve vendor | Pending vendors clearly listed. Documents viewable inline. Approve action immediate. | Hanamariam |  |  | UAT | Admin + UI | Must Have | Admin account, pending vendors | 3.2.3
UAT-17 | Admin rejects vendor | 1. View vendor detail 2. Click Reject 3. Enter reason in modal 4. Confirm 5. Verify status updated | Rejection modal appears. Reason required. Status changes immediately. | Hanamariam |  |  | UAT | Admin + UI | Must Have | Admin account, pending vendor | 3.4.2 UC14
UAT-18 | Admin suspends vendor | 1. Find verified vendor 2. Click Suspend 3. Confirm dialog 4. Verify vendor hidden from public | Suspension confirmed. Vendor no longer in public listing. | Hanamariam |  |  | UAT | Admin + UI | Must Have | Admin account, verified vendor | 4.11.3
UAT-19 | Admin manages users (future) | 1. Navigate to Users page 2. Search for user 3. View details 4. Ban user 5. Verify user cannot login | User management intuitive. Ban effective immediately. | Hanamariam |  |  | UAT | Admin + UI | Must Have | Admin users page implemented | US-A-001
UAT-20 | Admin views analytics (future) | 1. Navigate to Analytics 2. See dashboard with charts 3. View user registration trends 4. View vendor stats 5. View revenue data | Charts render correctly. Data accurate. Filters work. | Hanamariam |  |  | UAT | Admin + UI | Should Have | Analytics module implemented | 4.6.8

## Performance
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Load & Response Time
PT-01 | API response time (normal load) | 1. Run k6 with 50 virtual users for 5 minutes 2. Measure p50, p95, p99 response times for key endpoints | p95 < 1 second for all endpoints. p99 < 2 seconds. | Hanamariam |  |  | Performance | All | Must Have | Deployed backend with test data | 3.3.1
PT-02 | Vendor search response time | 1. Run 100 concurrent vendor search requests with filters 2. Measure response time | p95 < 800ms. Database indexes used effectively. | Hanamariam |  |  | Performance | Vendor | Must Have | 100+ vendors in DB | 3.3.1
PT-03 | WebSocket message latency | 1. Send 1000 messages between 50 concurrent connections 2. Measure delivery time | Average latency < 200ms. No dropped messages. | Hanamariam |  |  | Performance | Realtime | Should Have | Multiple connected users | 3.3.1
PT-04 | Concurrent user capacity | 1. Gradually ramp to 5000 virtual users 2. Monitor error rate and response times | System maintains < 1% error rate at 5000 users. Graceful degradation. | Hanamariam |  |  | Performance | All | Should Have | Scaled deployment | 3.3.1
PT-05 | Database query performance | 1. Run EXPLAIN ANALYZE on complex queries (vendor search, budget sums) 2. Check execution plans | No sequential scans on large tables. All queries < 500ms. | Hanamariam |  |  | Performance | Database | Should Have | Production-like dataset | 3.3.6
PT-06 | AI recommendation latency (future) | 1. Request recommendations with warm cache 2. Request with cold cache 3. Measure both | Warm cache: < 100ms. Cold cache: < 800ms. | Hanamariam |  |  | Performance | AI | Should Have | AI module + Redis implemented | 3.3.1
PT-07 | File upload throughput | 1. Upload 10 files concurrently (2-5MB each) 2. Measure upload time and success rate | All uploads succeed within 10 seconds. No timeouts. | Hanamariam |  |  | Performance | Vendor | Should Have | Supabase storage configured | 3.2.3
Stress & Endurance
PT-08 | Extended operation test | 1. Run moderate load (500 users) for 2 hours 2. Monitor memory, CPU, connection pools | No memory leaks. Stable CPU. Connection pools healthy. | Hanamariam |  |  | Performance | All | Should Have | Deployed system | 3.3.2
PT-09 | Socket.IO connection storm | 1. Rapidly connect/disconnect 500 clients within 30 seconds | Server handles gracefully. No crashes. Memory stable after connections close. | Hanamariam |  |  | Performance | Realtime | Should Have | Deployed Socket.IO server | 3.2.6
PT-10 | Database connection pool exhaustion | 1. Send concurrent requests exceeding pool size 2. Monitor behavior | Requests queue gracefully. No crashes. Errors returned after timeout. | Hanamariam |  |  | Performance | Database | Should Have | High concurrent load | 3.3.6

## Security
Test ID | Test Case Name | Description / Steps | Expected Result | Tester | Result | Notes | Test Type | Module | Priority | Prerequisites | Doc Reference
Authentication & Authorization
ST-01 | Session cookie security flags | 1. Login 2. Inspect cookie attributes in browser DevTools | httpOnly=true, SameSite=lax (or strict), Secure=true in production, path=/. | Sura |  |  | Security | Auth | Must Have | Running application | 4.11.1
ST-02 | Password storage verification | 1. Check database user table 2. Verify password field is hashed | Password stored as bcrypt/argon2 hash. Raw password never stored. | Sura |  |  | Security | Auth | Must Have | Database access | 3.3.3
ST-03 | Brute force login prevention | 1. Attempt 20 failed logins rapidly for same account | Account temporarily locked or requests throttled after N failures. | Sura |  |  | Security | Auth | Should Have | Running application | 3.3.3
ST-04 | Session fixation prevention | 1. Note session ID before login 2. Login 3. Check if session ID changed | New session generated on login. Old session invalidated. | Sura |  |  | Security | Auth | Must Have | Running application | 4.11.1
ST-05 | Privilege escalation - modify role | 1. Intercept API requests 2. Try to modify role field in request body | Role changes rejected. Server-side role enforcement unchanged. | Sura |  |  | Security | Auth | Must Have | Authenticated session | 4.11.4
Input Validation & Injection
ST-06 | SQL injection in vendor search | 1. GET /api/v1/vendors?search=' OR 1=1 -- 2. Check if all vendors returned or error | No SQL injection. Parameterized query returns empty or filtered results. | Sura |  |  | Security | Vendor | Must Have | Running application | 3.3.3
ST-07 | SQL injection in login | 1. POST /api/auth/sign-in with email: "' OR '1'='1" | Login fails. No database manipulation. | Sura |  |  | Security | Auth | Must Have | Running application | 3.3.3
ST-08 | XSS in chat messages | 1. Send message: <script>alert('XSS')</script> 2. Check if script executes in receiver's browser | Script not executed. Message displayed as escaped text. | Sura |  |  | Security | Realtime | Must Have | Running chat | 3.3.3
ST-09 | XSS in vendor profile | 1. Set vendor business_name to '<img src=x onerror=alert(1)>' 2. View profile in public listing | HTML not rendered. Displayed as plain text. | Sura |  |  | Security | Vendor | Must Have | Running application | 3.3.3
ST-10 | Path traversal in file upload | 1. Upload file with name '../../../etc/passwd' 2. Check storage location | File stored with sanitized name. No path traversal possible. | Sura |  |  | Security | Vendor | Must Have | Running application + Supabase | 3.3.3
ST-11 | NoSQL/JSON injection in profile update | 1. PATCH /api/v1/vendor/profile with malicious JSON payloads | Only whitelisted fields updated. Injected fields ignored. | Sura |  |  | Security | Vendor | Should Have | Running application | 3.3.3
Data Privacy & Access Control
ST-12 | User cannot read others' conversations | 1. Login as user A 2. GET /api/v1/conversations/:id (owned by user B) | 403 Forbidden. No conversation data leaked. | Sura |  |  | Security | Realtime | Must Have | Two users with separate conversations | 3.3.3
ST-13 | User cannot read others' notifications | 1. Guess notification IDs 2. PATCH /api/v1/notifications/:id/read for another user's notification | 403 or 404. Cannot modify others' notifications. | Sura |  |  | Security | Realtime | Must Have | Two users with notifications | 3.3.3
ST-14 | Vendor cannot access other vendor's profile data | 1. Login as vendor A 2. Attempt to GET /api/v1/vendor/profile (returns only own data) | Only own profile data returned. No IDOR vulnerability. | Sura |  |  | Security | Vendor | Must Have | Two vendor accounts | 3.3.3
ST-15 | Admin audit logging (future) | 1. Admin performs sensitive action (impersonate, ban) 2. Check audit log | Action logged with admin ID, target, timestamp, action type. | Sura |  |  | Security | Admin | Should Have | Admin module with audit logging | 4.11.3
API Security
ST-16 | CORS policy enforcement | 1. Make request from unauthorized origin 2. Check if blocked | Cross-origin requests from non-whitelisted domains blocked. | Sura |  |  | Security | All | Must Have | Running application | 3.3.3
ST-17 | Request size limits | 1. Send POST with extremely large body (>10MB JSON) | 413 Payload Too Large. Server not crashed. | Sura |  |  | Security | All | Must Have | Running application | 3.3.3
ST-18 | Rate limiting on auth endpoints | 1. Send 100 login requests in 10 seconds | Rate limited after threshold. 429 Too Many Requests. | Sura |  |  | Security | Auth | Should Have | Rate limiter configured | 3.3.3
ST-19 | HTTPS enforcement (production) | 1. Attempt HTTP connection to production server | Redirected to HTTPS. No data sent over plain HTTP. | Sura |  |  | Security | All | Must Have | Production deployment | 3.3.3
ST-20 | Sensitive data in error responses | 1. Trigger various errors 2. Check response bodies | No stack traces, internal paths, or sensitive info in error responses. | Sura |  |  | Security | All | Must Have | Running application | 3.3.3