## Overview
TWEDAR - Task Assignment Sheet
Feature Module Assignments for Chera, Abdi & Tamirat
ASSIGNEE LEGEND
Chera
Abdi
Tamirat
STATUS LEGEND
Done
In Progress
Not Started
MODULE ASSIGNMENTS
Module | Assignee | Total | Done | In Progress | Not Started | Completion %
1. Auth & User Mgmt | Chera | 18 | 14 | 3 | 1 | 78%
2. Vendor Management | Chera | 24 | 21 | 1 | 2 | 88%
3. Real-Time Comms | Chera | 16 | 13 | 0 | 3 | 81%
4. Budgeting & Expense | Abdi | 8 | 0 | 0 | 8 | 0%
5. AI Recommendations | Tamirat | 10 | 0 | 0 | 10 | 0%
6. Booking & Scheduling | Abdi | 8 | 0 | 0 | 8 | 0%
7. Payment Integration | Tamirat | 8 | 0 | 0 | 8 | 0%
8. Review & Feedback | Tamirat | 8 | 0 | 0 | 8 | 0%
9. Admin & Analytics | Chera | 12 | 2 | 4 | 6 | 17%
10. Couple Planning | Abdi | 11 | 0 | 1 | 10 | 0%
11. Non-Functional | Chera | 16 | 1 | 6 | 9 | 6%
TOTAL |  | 139 | 51 | 15 | 73 | 37%
PER-PERSON SUMMARY
Team Member |  | Total Tasks | Done | In Progress | Not Started | Completion %
Chera |  | 86 | 51 | 14 | 21 | 59%
Abdi |  | 27 | 0 | 1 | 26 | 0%
Tamirat |  | 26 | 0 | 0 | 26 | 0%

## 1. Auth & User Mgmt
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Registration & Login
A-01 | Email/Password Registration | Users register with email and password. | Chera | Done | Done | Done |  | Must Have | 3.2.1
A-02 | Email Verification | System sends verification email after registration. | Chera | Done | Done | Done |  | Must Have | 3.2.1
A-03 | Email/Password Login | Authenticated login with session cookie. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC2
A-04 | Google OAuth (Couples) | Social login via Google. | Chera | Done | Done | Done |  | Must Have | 3.2.1
A-05 | Apple OAuth (Couples) | Social login via Apple. | Chera | Done | Done | Done |  | Should Have | 3.2.1
A-06 | Password Reset / Forgot Password | Email-based password reset flow. | Chera | Done | Done | Done |  | Must Have | 3.2.1
Session & Security
A-07 | HTTP-Only Session Cookies | Secure session management. | Chera | Done | Done | Done |  | Must Have | 4.11.1
A-08 | RBAC Middleware | Role-based access control at API level. | Chera | Done | Done | Done |  | Must Have | 4.11.4
A-09 | Session Validation on App Load | Check session on initial page load. | Chera | Done | Done | Done |  | Must Have | 4.11.1
A-10 | 401 Global Handling | Redirect to login on unauthorized. | Chera | Done | Done | Done |  | Must Have | 4.11.1
Role Management
A-11 | Couple Role | Standard user with wedding planning access. | Chera | Done | Done | Done |  | Must Have | 4.11.4
A-12 | Vendor Owner Role | Organization owner with full vendor dashboard. | Chera | Done | Done | In Progress | Add organization member list UI, staff management. | Must Have | 4.11.4
A-13 | Vendor Staff Role | Organization member with limited access. | Chera | In Progress | Done | Not Started | Build vendor staff invitation UI, restricted staff dashboard. | Should Have | 4.11.4
A-14 | Super Admin Role | Full system access for platform management. | Chera | Done | Done | In Progress | Build admin users list, reports, and settings pages. | Must Have | 4.11.4
A-15 | Content Moderator Role | Limited admin privileges. | Chera | In Progress | In Progress | Not Started | Add moderator role assignment UI, restricted admin views. | Could Have | 4.11.4
Profile Management
A-16 | Couple Profile Update | Couples update personal info, wedding prefs. | Chera | In Progress | In Progress | Not Started | Build couple profile page with wedding date, theme, location fields. | Must Have | 3.4.2 UC3
A-17 | Vendor Profile Management | Vendors manage business info. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC3
A-18 | Admin Profile/Settings | Admin can update system settings. | Chera | Not Started | Not Started | Not Started | Build admin settings page and backend config API. | Could Have | 3.4.2 UC3

## 2. Vendor Management
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Vendor Profile & Listing
V-01 | Vendor Registration | Vendor registers and auto-creates organization. | Chera | Done | Done | Done |  | Must Have | 3.2.2
V-02 | Business Profile Creation | Vendor creates profile with business details. | Chera | Done | Done | Done |  | Must Have | 3.2.2
V-03 | Service & Pricing Packages | Vendor defines service types and pricing. | Chera | Done | Done | Done |  | Must Have | 3.2.2
V-04 | Location with Map | Vendor sets location with lat/long on map. | Chera | Done | Done | Done |  | Must Have | 3.2.2
V-05 | Portfolio Upload | Vendor uploads images/videos. | Chera | In Progress | Done | In Progress | Build dedicated portfolio page with media grid. | Must Have | 3.4.2 UC11
V-06 | Social Links | Vendor adds social media links. | Chera | Done | Done | Done |  | Could Have | 3.2.2
V-07 | Vendor Availability/Schedule | Vendor sets available dates and hours. | Chera | Not Started | Not Started | Not Started | Build availability schema, API endpoints, calendar UI. | Should Have | 3.2.2
Document & Verification
V-08 | Document Upload | Vendor uploads business documents. | Chera | Done | Done | Done |  | Must Have | 3.2.3
V-09 | Document Delete | Vendor removes uploaded documents. | Chera | Done | Done | Done |  | Must Have | 3.2.3
V-10 | Submit for Verification | Vendor submits profile for admin review. | Chera | Done | Done | Done |  | Must Have | 3.2.3
V-11 | Verification Status Display | Vendor sees verification status. | Chera | Done | Done | Done |  | Must Have | 3.2.3
V-12 | Resubmission After Rejection | Vendor fixes and resubmits. | Chera | Done | Done | Done |  | Should Have | 3.2.3
Admin Vendor Actions
V-13 | List All Vendors (Admin) | Admin views all vendors with status. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC14
V-14 | Approve Vendor | Admin approves vendor. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC14
V-15 | Reject Vendor | Admin rejects vendor with reason. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC14
V-16 | Suspend Vendor | Admin suspends vendor. | Chera | Done | Done | Done |  | Must Have | 4.11.3
V-17 | Reinstate Vendor | Admin reactivates suspended vendor. | Chera | Done | Done | Done |  | Should Have | 4.11.3
V-18 | Deactivate Vendor | Admin permanently deactivates vendor. | Chera | Done | Done | Done |  | Should Have | 4.11.3
Public Vendor Discovery
V-19 | Public Vendor Listing | Couples browse verified vendors. | Chera | Done | Done | Done |  | Must Have | 3.2.2
V-20 | Vendor Detail Page | Couples view full vendor profile. | Chera | Done | Done | Done |  | Must Have | 3.4.2 UC8
V-21 | Vendor Filtering by Category | Filter by service type. | Chera | Done | Done | Done |  | Must Have | US-C-004
V-22 | Vendor Filtering by Location | Filter by city/area. | Chera | Done | Done | Done |  | Must Have | US-C-004
V-23 | Vendor Filtering by Verification | Show only verified vendors. | Chera | Done | Done | Done |  | Must Have | US-C-007
V-24 | Save Vendors to Favorites | Couple saves vendors for later. | Chera | Not Started | Not Started | Not Started | Build favorites table, API, heart button in vendor cards. | Could Have | US-C-008

## 3. Real-Time Comms
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Socket.IO Infrastructure
R-01 | Socket.IO Server Setup | WebSocket server with auth. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-02 | Socket.IO Client Connection | Frontend authenticated WS connection. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-03 | Room-based Architecture | Users join/leave rooms. | Chera | Done | Done | Done |  | Must Have | 3.2.6
Chat / Messaging
R-04 | Create Conversation | Couple initiates conversation with vendor. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-05 | List Conversations | User sees all conversations. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-06 | Send Text Message | Real-time text message delivery. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-07 | Message History | Load previous messages. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-08 | Typing Indicators | Show when other user is typing. | Chera | Done | Done | Done |  | Should Have | Scenario 4
R-09 | Read Receipts | Mark messages as read. | Chera | Done | Done | Done |  | Should Have | Scenario 4
R-10 | File Attachments in Chat | Send files in chat. | Chera | Not Started | Not Started | Not Started | Add file upload for chat, message type field, file preview. | Should Have | US-C-017
Notifications
R-11 | In-App Notifications | Real-time notification delivery. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-12 | Notification REST API | Fetch and mark notifications. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-13 | Notification Bell/Badge | Visual unread indicator. | Chera | Done | Done | Done |  | Must Have | 3.2.6
R-14 | Push Notifications | Notifications when app is closed. | Chera | Not Started | Not Started | Not Started | Integrate Web Push API / FCM for background notifications. | Should Have | US-C-018
R-15 | Email Notifications | Email alerts for critical events. | Chera | Not Started | Not Started | Not Started | Extend email service for booking, payment, reminders. | Could Have | 3.2.6
Presence
R-16 | User Online/Offline Status | Show if user is online. | Chera | Done | Done | Done |  | Could Have | 3.2.6

## 4. Budgeting & Expense
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Budget Planning
B-01 | Create Wedding Budget | Couple defines total budget. | Abdi | Not Started | Not Started | Not Started | Create budget table, API, budget creation UI. | Must Have | 3.2.5
B-02 | Budget Category Allocation | Allocate budget into categories. | Abdi | Not Started | Not Started | Not Started | Create budget_categories table, CRUD API, allocation UI. | Must Have | 3.2.5
B-03 | AI-Suggested Budget Allocation | System suggests category distribution. | Abdi | Not Started | Not Started | Not Started | Build recommendation logic, API, suggestion UI. | Should Have | 3.2.5
Expense Tracking
B-04 | Add Expense Entry | Record expenses against categories. | Abdi | Not Started | Not Started | Not Started | Create expenses table, API, expense form UI. | Must Have | 3.2.5
B-05 | Real-Time Budget Totals | Live spending vs allocated amounts. | Abdi | Not Started | Not Started | Not Started | Build budget summary calculations, progress bars UI. | Must Have | 3.2.5
B-06 | Budget Alerts & Limits | Warnings when spending approaches limits. | Abdi | Not Started | Not Started | Not Started | Add threshold logic, notification triggers, alert banners. | Should Have | 3.2.5
B-07 | Receipt Upload | Attach receipt images to expenses. | Abdi | Not Started | Not Started | Not Started | Add receipt storage, upload API, receipt preview. | Could Have | US-C-013
B-08 | Budget Summary Reports | Generate exportable reports. | Abdi | Not Started | Not Started | Not Started | Build report API, PDF/CSV export, report page. | Could Have | US-C-014

## 5. AI Recommendations
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Recommendation Engine
AI-01 | Content-Based Filtering | Recommend vendors using attributes. | Tamirat | Not Started | Not Started | Not Started | Build vendor vectorization, similarity scoring, API. | Must Have | 3.2.4
AI-02 | Collaborative Filtering | Recommend based on similar couples. | Tamirat | Not Started | Not Started | Not Started | Build interaction tracking, matrix factorization. | Should Have | 3.2.4
AI-03 | Hybrid Weighted Approach | Combine content + collaborative. | Tamirat | Not Started | Not Started | Not Started | Implement weighted scoring with adaptive weights. | Should Have | 3.2.4
AI-04 | Cold-Start Handling | Meaningful recommendations with zero data. | Tamirat | Not Started | Not Started | Not Started | Default to content-based, use metadata + preferences. | Must Have | 3.2.4
AI-05 | User Preference Collection | Gather couple preferences. | Tamirat | Not Started | Not Started | Not Started | Build preference wizard, user_preferences table. | Must Have | 3.2.4
Caching & Performance
AI-06 | Redis Recommendation Cache | Cache recommendations for 24h. | Tamirat | Not Started | Not Started | Not Started | Add Redis, cache layer, TTL-based invalidation. | Must Have | 4.6.3
AI-07 | Cache Invalidation Rules | Invalidate on preference/booking/profile change. | Tamirat | Not Started | Not Started | Not Started | Implement cache key strategy, event-driven invalidation. | Should Have | 4.6.3
AI-08 | Sub-2-Second Response | Results within 2 seconds. | Tamirat | Not Started | Not Started | Not Started | Optimize queries, pre-compute scores, use Redis. | Must Have | 3.3.1
Recommendation UI
AI-09 | Recommendation Badges | Highlight top-matched vendors. | Tamirat | Not Started | Not Started | Not Started | Add badge component, match score display. | Should Have | Scenario 5
AI-10 | Personalized Vendor Search | AI-ranked search results. | Tamirat | Not Started | Not Started | Not Started | Integrate AI scoring into search pipeline. | Must Have | Scenario 5

## 6. Booking & Scheduling
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Booking Workflow
BK-01 | Send Booking Request | Couple submits booking request. | Abdi | Not Started | Not Started | Not Started | Create bookings table, API, booking request form. | Must Have | 3.4.2 UC9
BK-02 | Vendor Reviews Booking | Vendor sees incoming requests. | Abdi | Not Started | Not Started | Not Started | Build vendor bookings list, incoming requests page. | Must Have | 3.4.2 UC9
BK-03 | Accept/Decline Booking | Vendor accepts or declines. | Abdi | Not Started | Not Started | Not Started | Add booking status machine, status update API. | Must Have | 3.4.2 UC9
BK-04 | Booking Status Tracking | Both parties see booking status. | Abdi | Not Started | Not Started | Not Started | Build booking detail page with status timeline. | Must Have | 3.4.2 UC9
BK-05 | Booking Confirmation Notification | Notify couple on accept/decline. | Abdi | Not Started | Not Started | Not Started | Wire booking status changes to notification service. | Must Have | US-C-018
Scheduling & Calendar
BK-06 | Vendor Availability Calendar | Vendors set available/blocked dates. | Abdi | Not Started | Not Started | Not Started | Build availability_slots table, calendar API and UI. | Should Have | 3.2.2
BK-07 | Date Conflict Detection | Prevent double-booking. | Abdi | Not Started | Not Started | Not Started | Add unique constraint on vendor+date, validation. | Should Have | 3.2.2
BK-08 | Booking History | Past and upcoming bookings list. | Abdi | Not Started | Not Started | Not Started | Build booking list API, history pages. | Must Have | US-C-021

## 7. Payment Integration
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Payment Integration
P-01 | Chapa Payment Gateway | Integrate Chapa API. | Tamirat | Not Started | Not Started | Not Started | Add Chapa SDK, payment API, webhook handler. | Must Have | 3.2.7
P-02 | Telebirr Integration | Support Telebirr mobile money. | Tamirat | Not Started | Not Started | Not Started | Research Telebirr API, implement adapter. | Should Have | 3.2.7
P-03 | CBE Birr Integration | Support CBE Birr payments. | Tamirat | Not Started | Not Started | Not Started | Research CBE Birr API, implement adapter. | Could Have | 3.2.7
Payment Workflow
P-04 | Advance Deposit Payment | Couple makes deposit to secure booking. | Tamirat | Not Started | Not Started | Not Started | Build deposit flow with gateway redirect + webhook. | Must Have | 3.2.7
P-05 | Final Payment | Complete remaining payment. | Tamirat | Not Started | Not Started | Not Started | Build final payment trigger, amount calculation. | Must Have | 3.2.7
P-06 | Escrow-Style Workflow | Hold funds until service delivered. | Tamirat | Not Started | Not Started | Not Started | Design escrow state machine, hold/release/refund. | Should Have | 3.2.7
P-07 | Payment History | View all transactions. | Tamirat | Not Started | Not Started | Not Started | Build payments table, transaction history API and page. | Must Have | 3.2.7
P-08 | Payment-Expense Linkage | Auto-record payments as budget expenses. | Tamirat | Not Started | Not Started | Not Started | Link payment confirmation to expense creation. | Should Have | 3.2.7

## 8. Review & Feedback
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Review Submission
RV-01 | Submit Rating & Review | Couple rates vendor with stars and text. | Tamirat | Not Started | Not Started | Not Started | Create reviews table, API, review form UI. | Must Have | 3.2.8
RV-02 | One Review Per Booking | Prevent duplicate reviews. | Tamirat | Not Started | Not Started | Not Started | Add unique constraint on booking_id. | Must Have | 3.2.8
RV-03 | Photo Upload with Review | Couple uploads photos as feedback. | Tamirat | Not Started | Not Started | Not Started | Add review_photos table, image upload, gallery. | Could Have | US-C-023
Review Management
RV-04 | Vendor Rating Aggregation | Auto-calculate average rating. | Tamirat | Not Started | Not Started | Not Started | Build trigger to recalculate avg on new review. | Must Have | 3.2.8
RV-05 | Admin Review Moderation | Admin approves/removes reviews. | Tamirat | Not Started | Not Started | Not Started | Add isApproved field, admin queue API, moderation UI. | Must Have | 3.4.2 UC15
RV-06 | Review Display on Vendor Profile | Show reviews on public vendor page. | Tamirat | Not Started | Not Started | Not Started | Fetch reviews, display review cards with stars. | Must Have | 3.2.8
RV-07 | Review Feeds AI Recommendations | Use review data for collaborative filtering. | Tamirat | Not Started | Not Started | Not Started | Include review scores in recommendation matrix. | Should Have | 3.2.4
RV-08 | Vendor Notification on New Review | Notify vendor on new review. | Tamirat | Not Started | Not Started | Not Started | Wire review creation to notification service. | Should Have | Scenario 3

## 9. Admin & Analytics
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
User Management
AD-01 | View All Users | Admin sees all registered users. | Chera | In Progress | In Progress | Not Started | Build admin users list page with filters. | Must Have | US-A-001
AD-02 | Suspend/Ban User | Admin suspends or bans accounts. | Chera | In Progress | Done | Not Started | Build user action buttons, confirmation dialogs. | Must Have | US-A-002
AD-03 | Reactivate User | Admin reactivates suspended accounts. | Chera | In Progress | Done | Not Started | Add reactivate button, confirmation flow. | Should Have | US-A-003
AD-04 | Impersonate User Session | Admin views platform as specific user. | Chera | In Progress | Done | Not Started | Build impersonation button, exit-impersonation banner. | Could Have | US-A-004
Vendor Verification (Admin)
AD-05 | Vendor Verification Dashboard | Dedicated vendor review panel. | Chera | Done | Done | Done |  | Must Have | 3.2.3
AD-06 | Document Review Interface | View uploaded vendor docs inline. | Chera | Done | Done | Done |  | Must Have | 3.2.3
Analytics & Reporting
AD-07 | Platform Analytics Dashboard | User counts, vendor stats, booking volume. | Chera | Not Started | Not Started | Not Started | Build analytics queries, stats API, charts. | Should Have | 4.6.8
AD-08 | Revenue Reports | Track platform revenue. | Chera | Not Started | Not Started | Not Started | Build revenue aggregation, report generation. | Could Have | 4.6.8
AD-09 | User Activity Reports | Monitor engagement, trends. | Chera | Not Started | Not Started | Not Started | Build activity logging, trend calculations. | Could Have | 4.6.8
AD-10 | System Health Monitoring | Uptime, response times, error rates. | Chera | Not Started | Not Started | Not Started | Integrate monitoring, build status page. | Should Have | 3.3.2
Content Moderation
AD-11 | Review Moderation Queue | Admin reviews user reviews. | Chera | Not Started | Not Started | Not Started | Build moderation queue, approve/reject actions. | Must Have | 3.4.2 UC15
AD-12 | Content Moderator Role | Assign limited admin privileges. | Chera | Not Started | Not Started | Not Started | Add role assignment UI, moderator permissions. | Could Have | 4.11.3

## 10. Couple Planning
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Wedding Project
C-01 | Create Wedding Plan | Initialize wedding with date, location, theme. | Abdi | Not Started | Not Started | Not Started | Create wedding_projects table, CRUD API, setup wizard. | Must Have | 3.4.2 UC4
C-02 | Wedding Profile Customization | Set and update wedding preferences. | Abdi | Not Started | Not Started | Not Started | Build preferences page with theme, style, location. | Must Have | US-C-003
C-03 | Wedding Dashboard | Central overview of planning progress. | Abdi | In Progress | In Progress | In Progress | Connect dashboard stats to real data. | Must Have | 3.4.1
Checklist & Timeline
C-04 | Wedding Checklist | Pre-built and custom task checklist. | Abdi | Not Started | Not Started | Not Started | Build checklist_items table, CRUD API, checklist page. | Must Have | 1.5.1
C-05 | Task Deadlines & Reminders | Due dates with reminders. | Abdi | Not Started | Not Started | Not Started | Add due_date field, reminder triggers, overdue highlighting. | Should Have | 1.5.1
C-06 | Planning Timeline/Milestones | Visual timeline of milestones. | Abdi | Not Started | Not Started | Not Started | Build milestone model, timeline visualization. | Could Have | 1.5.1
Guest Management
C-07 | Guest List | Manage invited guests. | Abdi | Not Started | Not Started | Not Started | Build guests table, CRUD API, guest list page. | Must Have | 1.5.1
C-08 | RSVP Tracking | Track guest responses. | Abdi | Not Started | Not Started | Not Started | Add RSVP status, guest-facing RSVP page. | Should Have | 1.5.1
C-09 | Guest Count & Seating | Track guests and seating. | Abdi | Not Started | Not Started | Not Started | Build seating plan model, table assignment UI. | Could Have | 1.5.1
Discovery & Favorites
C-10 | Vendor Favorites List | Save vendors to compare. | Abdi | Not Started | Not Started | Not Started | Build favorites table, toggle API, favorites page. | Could Have | US-C-008
C-11 | Vendor Comparison | Side-by-side comparison. | Abdi | Not Started | Not Started | Not Started | Build comparison view with key metrics. | Could Have | US-C-005

## 11. Non-Functional
ID | Feature Name | Description | Assignee | Status | Backend | Frontend | Remaining Work | Priority | Doc Reference
Performance
NF-01 | Sub-2-Second Response Time | 95% of requests respond within 1s. | Chera | In Progress | In Progress | In Progress | Add monitoring, load testing, optimize queries. | Must Have | 3.3.1
NF-02 | 5000 Concurrent Users | System supports 5000+ users. | Chera | Not Started | Not Started | Not Started | Load test, configure scaling, optimize WebSocket. | Should Have | 3.3.1
NF-03 | Recommendation < 800ms | AI recommendations within 800ms. | Chera | Not Started | Not Started | Not Started | Depends on Redis caching once AI is built. | Should Have | 3.3.1
Security
NF-04 | HTTPS/TLS Encryption | All communication encrypted. | Chera | In Progress | In Progress | In Progress | Configure TLS for production. | Must Have | 3.3.3
NF-05 | Data Encryption at Rest | Sensitive fields encrypted. | Chera | Not Started | Not Started | Not Started | Identify PII, implement encryption layer. | Should Have | 3.3.3
NF-06 | Input Validation (OWASP) | All inputs validated. | Chera | In Progress | In Progress | In Progress | Add Zod/Joi validation on all endpoints. | Must Have | 3.3.3
NF-07 | SQL Injection Prevention | Parameterized queries throughout. | Chera | Done | Done | Done |  | Must Have | 3.3.3
Reliability & Availability
NF-08 | 99.5% Monthly Uptime | System available 99.5%. | Chera | Not Started | Not Started | Not Started | Configure health checks, monitoring alerts. | Should Have | 3.3.2
NF-09 | Daily Automated Backups | PostgreSQL backup RPO <= 24h. | Chera | Not Started | Not Started | Not Started | Configure automated backups, verify PITR. | Should Have | 3.3.2
NF-10 | Disaster Recovery (RTO <= 4h) | Recover within 4 hours. | Chera | Not Started | Not Started | Not Started | Document recovery, test backup restoration. | Should Have | 3.3.2
Scalability & Infrastructure
NF-11 | Horizontal Backend Scaling | Backend supports multiple instances. | Chera | In Progress | In Progress | Not Started | Add Socket.IO Redis adapter, load balancer. | Should Have | 3.3.6
NF-12 | Database Indexing & Caching | Efficient queries with indexes. | Chera | In Progress | In Progress | Not Started | Add Redis for frequent data, optimize queries. | Should Have | 3.3.6
NF-13 | Cloud Deployment | Deploy to AWS/GCP/Vercel. | Chera | Not Started | Not Started | Not Started | Configure CI/CD pipeline, deploy. | Should Have | 5.5
Mobile & Accessibility
NF-14 | Flutter Mobile App | Cross-platform mobile app. | Chera | Not Started | Not Started | Not Started | Initialize Flutter project, implement core screens. | Should Have | 1.11
NF-15 | Responsive Web UI | Works on mobile and tablets. | Chera | In Progress | Done | In Progress | Test all pages on mobile, fix responsive issues. | Must Have | 3.3.4
NF-16 | Accessibility Standards | WCAG compliance. | Chera | Not Started | Not Started | Not Started | Add ARIA labels, keyboard navigation, screen reader. | Should Have | 3.3.4